## 0.Key offshore logistics
Operations phase
Floating substation

## 1.Surveys
Initial and subsequent surveys to determine resource potential, metocean, environmental, seabed and soil conditions/limitations as basis for mooring system design,dimensioning and installation methods
Main task |  | Environmental survey | Resource/metocean survey: Floting metmast installation? | Resource/metocean survey: buoy and sensors installation | Resource/metocean survey: Sensor operation and maintenance | Geophysical survey | Geotechnical survey
Activity description |  | To determine the environmental impacts, a full suite of environmental surveys of the wind farm location and its surroundings is undertaken. These surveys establish the baseline for the assessment and allow impact modelling to be undertaken. The surveys include bird, fish, marine mammal and habitat surveys as well as marine navigation studies, socio-economic surveys, commercial fishing, archaeology, noise analysis, landscape and visual assessment and aviation impact assessments. Environmental surveys are typically undertaken by companies from the home market, partly because there is sufficient local resource and partly because some of the wildlife impacts are site specific and require detailed local knowledge and expertise. | Towing from port. Mooring system installation | Installation of met-mast (foundation, mast, platform) and buoys to support sensor for the gathering of metocean data. wind speed,wind direction, wave, current, sealevel, temperature, pressure, humidity, solar radiation and visibility. Bird radar and hydrophones detecting cetacean activity can provide additional information to vessel and air-based environmental surveys. | Maintenance, including inspection, cleaning (of e.g PV panels and equipment) and refuelling (where diesel generators or hydrogen fuel cells or similar are used). | Geophysical surveys establish sea floor bathymetry, sea bed features, water depth and soil stratigraphy, as well as identifying hazardous areas on the seafloor and manmade risks such as unexploded ordnance (UXO). All considering the seabed positioning of anchors and cables. Hydrographic surveys examine the impact of the wind farm development on local sedimentation and coastal processes such as erosion. Geophysical surveys are non-intrusive and include remote sensing techniques such as seismic methods, echo sounding and magnetometry. | Geotechnical studies are predominantly intrusive and include such methods as boreholes with soil/rock sampling, and cone penetration testing (CPT). CPT are made in way of representative area for the entire balance of plant (anchors and cables in this context)
Vessel |  |  | Tug boat/AHTS | Smaller vessels for wave buoys, sensor installation. | Access vessel /Crew transfer vessel | Survey vessel | Survey vessel
Estimated dayrate |  | 2500-4500 £ | Tug: 5000-7000 £ AHTS: 8000-30.000 £ | 5000-10.000 £ | 2500-4500 £ | 19.000-26.000 £ | 19.000-26.000 £
[6 empty] | May also be the same as for geotechnical survey | May also be the same as for geophysical survey
Vessel main characteristics |  | Vessels should provide a stable viewing platform so vessel length and height are important considerations. |  |  | Good seakeeping abilities to support W2W | The vessels provide a stable platform for the survey/mapping activities. Long endurance for campaigns lasting about one month. | The vessels provide a stable platform for the acquisition of samples and in-situ testing. Long endurance for campaigns lasting about one month. Equipped with deck cranes, A-frame and/or moonpool. Smaller jack-ups may be effective for the smaling purpose
Critical vessel equipment/technology |  | None governing the vessel dimensions or capability other than very generic (stability, operability) |  | None governing the vessel dimensions or capability other than very generic (stability, operability) | Operability in 2.5 mHs(?) W2W for 3.5 m Hs | A-frame ROV hangar? <25 years(?) Endurance > 30 days | A-frame ROV hangar? <25 years(?) Endurance > 30 days
Intl suppliers |  | APEM, ECON, ESS Ecology, Fugro, Gardline Marine Services, HiDef Aerial Surveying, Natural Power, RPS. |  |  | Fugro, Gardline Marine Services, Natural Power, Precision Marine. | Bibby HydroMap, Fugro, Gardline Marine Services, Horizon and MMT. | Fugro, G-tec, Gardline Marine Services and Horizon.
Norwegian suppliers
Market share
Trend |  | Traditional visual surveys using boat and aerial platforms are being supplemented or replaced by new, more accurate technologies such as static and towed acoustic monitoring, tagging of individuals with satellite transmitters and remotely controlled video monitoring. |  | Floating lidar . A number of offshore wind developers have successfully designed, financed and constructed projects based solely on lidar data.
Nor Market potential
Sub-task | [5 empty] | UXO scan (magnetometer) | Sample analysis in offshore laboratory
Bathymetric survey (multibeam echo sounder, side scan sonar, acoutic seimsmic profiling)
marine archaeological survey, involving archaeological experts
filters in the vessel list activated |  | The vessel S/L Bintang is a small 25ft vessel, they have done such work and are one | Unable to find any vessels which have done this type of job. | We hired in the Island Valiant earlier this year. | The Odfjell wind vessels, they can perform in 2.0 m Hs which have been the latest requiremetns in England according to Odfjel | Specific track record for bottom survey, the term geophysical or geotechincal is not used in the track records | Specific track record for bottom survey, the term geophysical or geotechincal is not used in the track records
Vessels - having been involved in wind project |  | S/L Bintang | none? | Island Valiant - set buoys for fish farm, same type of buoys | Fob Swath 1 | Larissa | Larissa
[5 empty] | Fob Swath 2 | Despina | Despina
[5 empty] | Fob Swath 3 | Havila Subsea | Havila Subsea
[5 empty] | Fob Swath 4 | MV Island Pride | MV Island Pride
[5 empty] | Fob Swath 5 | Polar King | Polar King
[5 empty] | Fob Swath 6 | Olympic Zeus | Olympic Zeus
[5 empty] | Fob Swath 7 | Olympic Taurus | Olympic Taurus
[5 empty] | Fob Swath 8 | Olympic Commander | Olympic Commander
[5 empty] | Fob Swath 9 | Olympic Intervention IV | Olympic Intervention IV
[6 empty] | Olympic Ares | Olympic Ares
[6 empty] | Olympic Challenger | Olympic Challenger
[6 empty] | Olympic Artemis | Olympic Artemis
[6 empty] | Olympic Delta | Olympic Delta
[6 empty] | Edda Flora | Edda Flora
[6 empty] | Stril Server | Stril Server
filters in the vessel list activated |  | No expensive vessels, i.e. no PSVs, AHTS, etc. Included: Service vessels, work boats, smaller cheaper boats. Tugs with less than 30 ton bollard pull are included because of price | Smaller vessels with crane >1 ton, have included vessels with 100 ton and smaller due to price. | Smaller vessels with crane >1 ton, have included vessels with 100 ton and smaller due to price. | Included: W2W, PSV, AHTS, IMR. Not: subsea vessels, large construction, tugs, small vessels | Included: AHTS with ROV, construction with ROV, PSV with potential A-frame (ROV in container), subsea with ROV Not included: smaller vessels, vessel with no crane nor potential a-frame | Included: AHTS with ROV, construction with ROV, PSV with potential A-frame (ROV in container), subsea with ROV Not included: smaller vessels, vessel with no crane nor potential a-frame
Vessels - capable of doing jobs
|  | Fosnakongen | Fosnakongen | Fosnakongen | Ocean Art | Ocean Art | Ocean Art
|  | Fosna Neptun | Fosna Neptun | Fosna Neptun | Ocean Alden | Ocean Alden | Ocean Alden
|  | Fosna Viking | Fosna Viking | Fosna Viking | Ocean Star | Ocean Star | Ocean Star
|  | Fosna Amon | Fosna Amon | Fosna Amon | Ocean Ness | Ocean Ness | Ocean Ness
|  | Fosna Aqua | Fosna Aqua | Fosna Aqua | Ocean Don | Ocean Don | Ocean Don
|  | Fjordbris | Fjordbris | Fjordbris | Ocean Tay | Ocean Tay | Ocean Tay
|  | Fosnakallen | Fosnakallen | Fosnakallen | Ocean Marlin | Ocean Marlin | Ocean Marlin
|  | Fosna | Fosna | Fosna | Ocean Osprey | Ocean Osprey | Ocean Osprey
|  | Fosna Atlas | Fosna Atlas | Fosna Atlas | Bourbon Orca | Bourboun Arctic | Bourboun Arctic
|  | Fosna Ares | Fosna Ares | Fosna Ares | Bourboun Arctic | Skandi Carla | Skandi Carla
|  | Fosna Orion | Fosna Orion | Fosna Orion | Bourbon Calm | Skandi Vinland | Skandi Vinland
|  | Fosna Fighter | Fosna Fighter | Fosna Fighter | Bourbon Clear | Skandi Amazonas | Skandi Amazonas
|  | Fosna Triton | Ocean Art | Ocean Art | Bourbon Front | Skandi Angra | Skandi Angra
|  | Fosna Poseidon | Ocean Response | Ocean Response | Bourbon Hidra | Skandi Atlantic | Skandi Atlantic
|  | Fosna Flyer | Ocean Alden | Ocean Alden | Bourbon Mistral | Skandi Bergen | Skandi Bergen
|  | Bjønn | Ocean Star | Ocean Star | Bourbon Monsoon | Skandi Botafogo | Skandi Botafogo
|  | Bebe | Ocean Ness | Ocean Ness | Bourbon Rainbow | Skandi Emerald | Skandi Emerald
|  | Buddy | Ocean Don | Ocean Don | Bourbon Sapphire | Skandi Fluminense | Skandi Fluminense
|  | Thor III | Ocean Tay | Ocean Tay | Bourbon Tampen | Skandi Hera | Skandi Hera
|  | Brage | Ocean Marlin | Ocean Marlin | Bourbon Topaz | Skandi Iceman | Skandi Iceman
|  | Beagle | Ocean Osprey | Ocean Osprey | Bourbon Emerald | Skandi Iguacu | Skandi Iguacu
|  | Bison | Bourbon Orca | Bourbon Orca | Bourbon Jade | Skandi Ipanema | Skandi Ipanema
|  | Bryteren | Bourboun Arctic | Bourboun Arctic | Bourbon Oceanteam 101 | Skandi Pacific | Skandi Pacific
|  | Christina E | Bourbon Hidra | Bourbon Hidra | Bourbon Opale | Skandi Paraty | Skandi Paraty
|  | M/B Ping | Bourbon Mistral | Bourbon Mistral | Southern Ocean (ex BO104) | Skandi Peregrino | Skandi Peregrino
|  | Fox | Bourbon Monsoon | Bourbon Monsoon | BB Octopus | Skandi Rio | Skandi Rio
|  | Lynx | Bourbon Sapphire | Bourbon Sapphire | BB Ocean | Skandi Saigon | Skandi Saigon
|  | Ibex | Bourbon Tampen | Bourbon Tampen | BB Lifter | Skandi Urca | Skandi Urca
|  | Max | Bourbon Topaz | Bourbon Topaz | Deep Endeavour | Skandi Vega | Skandi Vega
|  | Obelix | Bourbon Emerald | Bourbon Emerald | Deep Vision | Skandi Aukra | Skandi Aukra
|  | Oryx | Bourbon Jade | Bourbon Jade | Skandi Admiral (ex. Northern Admiral) | Skandi Barra | Skandi Barra
|  | Rex | Bourbon Oceanteam 101 | Bourbon Oceanteam 101 | Skandi Carla | Skandi Buchan | Skandi Buchan
|  | Trix | Bourbon Opale | Bourbon Opale | Skandi Vinland | Skandi Caledonia | Skandi Caledonia
|  | H U Sverdrup II | BB Octopus | BB Octopus | Skandi Amazonas | Skandi Captain | Skandi Captain
|  | M/S Nautilus | BB Ocean | BB Ocean | Skandi Angra | Skandi Feistein | Skandi Feistein
|  | M/S Nautilus Survey | BB Lifter | BB Lifter | Skandi Atlantic | Skandi Flora | Skandi Flora
|  | M/S Nautilus Ocean | Arbol Grande | Arbol Grande | Skandi Bergen | Skandi Foula | Skandi Foula
|  | M/S Nautilus Aldra | Deep Vision | Deep Vision | Skandi Botafogo | Skandi Gamma | Skandi Gamma
|  | Stril Poseidon | Skandi Admiral (ex. Northern Admiral) | Skandi Admiral (ex. Northern Admiral) | Skandi Emerald | Skandi Kvitsøy | Skandi Kvitsøy
|  | "Målebåt" (19 fots buster med utstyr) | Geograph | Geograph | Skandi Fluminense | Skandi Marøy | Skandi Marøy
|  | Tronds Max | Geoholm | Geoholm | Skandi Hera | Skandi Mongstad | Skandi Mongstad
|  |  | Geosea | Geosea | Skandi Iceman | Skandi Nova | Skandi Nova
|  |  | Geosund | Geosund | Skandi Iguacu | Skandi Rona | Skandi Rona
|  |  | Skandi Acu | Skandi Acu | Skandi Ipanema | Skandi Sotra | Skandi Sotra
|  |  | Skandi Buzios | Skandi Buzios | Skandi Pacific | Skandi Texel | Skandi Texel
|  |  | Skandi Carla | Skandi Carla | Skandi Paraty | NS Orla | NS Orla
|  |  | Skandi Chieftain | Skandi Chieftain | Skandi Peregrino | FS Frayja | FS Frayja
|  |  | Skandi Commander | Skandi Commander | Skandi Rio | Seven Viking | Seven Viking
|  |  | Skandi Constructor | Skandi Constructor | Skandi Saigon | Viking Queen | Viking Queen
|  |  | Skandi Darwin | Skandi Darwin | Skandi Urca | Viking Athene | Viking Athene
|  |  | Skandi Hawk | Skandi Hawk | Skandi Vega | Viking Avant | Viking Avant
|  |  | Skandi Hercules | Skandi Hercules | Skandi Aukra | Viking Energy | Viking Energy
|  |  | Skandi Hugen | Skandi Hugen | Skandi Barra | Viking Lady | Viking Lady
|  |  | Skandi Niteroi | Skandi Niteroi | Skandi Buchan | Viking Prince | Viking Prince
|  |  | Skandi Olinda | Skandi Olinda | Skandi Caledonia | Viking Princess | Viking Princess
|  |  | Skandi Olympia | Skandi Olympia | Skandi Captain | Christina E | Christina E
|  |  | Skandi Patagonia | Skandi Patagonia | Skandi Feistein | Polar Queen | Polar Queen
|  |  | Skandi Recife | Skandi Recife | Skandi Flora | Energy Duchess | Energy Duchess
|  |  | Skandi Vinland | Skandi Vinland | Skandi Foula | Energy Empress | Energy Empress
|  |  | Skandi Amazonas | Skandi Amazonas | Skandi Gamma | Larissa | Larissa
|  |  | Skandi Angra | Skandi Angra | Skandi Kvitsøy | Despina | Despina
|  |  | Skandi Atlantic | Skandi Atlantic | Skandi Marøy | Energy Swan | Energy Swan
|  |  | Skandi Bergen | Skandi Bergen | Skandi Mongstad | Energy Scout | Energy Scout
|  |  | Skandi Botafogo | Skandi Botafogo | Skandi Nova | Havila Mercury | Havila Mercury
|  |  | Skandi Emerald | Skandi Emerald | Skandi Rona | Havila Mars | Havila Mars
|  |  | Skandi Fluminense | Skandi Fluminense | Skandi Sotra | Havila Venus | Havila Venus
|  |  | Skandi Iceman | Skandi Iceman | Skandi Texel | Havila Jupiter | Havila Jupiter
|  |  | Skandi Iguacu | Skandi Iguacu | NS Orla | Havila Neptune | Havila Neptune
|  |  | Skandi Ipanema | Skandi Ipanema | FS Frayja | Havila Charisma | Havila Charisma
|  |  | Skandi Pacific | Skandi Pacific | Seven Viking | Havila Borg | Havila Borg
|  |  | Skandi Paraty | Skandi Paraty | Viking Queen | Havila Foresight | Havila Foresight
|  |  | Skandi Peregrino | Skandi Peregrino | Viking Athene | Havila Fortune | Havila Fortune
|  |  | Skandi Rio | Skandi Rio | Viking Avant | Havila Crusader | Havila Crusader
|  |  | Skandi Saigon | Skandi Saigon | Viking Energy | Havila Commander | Havila Commander
|  |  | Skandi Urca | Skandi Urca | Viking Lady | Havila Aurora | Havila Aurora
|  |  | Skandi Vega | Skandi Vega | Viking Prince | Havila Fanø | Havila Fanø
|  |  | Skandi Aukra | Skandi Aukra | Viking Princess | Havila Herøy | Havila Herøy
|  |  | Skandi Barra | Skandi Barra | Christina E | Havila Clipper | Havila Clipper
|  |  | Skandi Buchan | Skandi Buchan | Polar Queen | Havila Troll | Havila Troll
|  |  | Skandi Caledonia | Skandi Caledonia | Energy Duchess | MV Island Defender | MV Island Defender
|  |  | Skandi Captain | Skandi Captain | Energy Empress | MV Island Endeavour | MV Island Endeavour
|  |  | Skandi Feistein | Skandi Feistein | Larissa | MV Island Empress | MV Island Empress
|  |  | Skandi Flora | Skandi Flora | Despina | MV Island Duchess | MV Island Duchess
|  |  | Skandi Foula | Skandi Foula | Energy Swan | MV Island Dragon | MV Island Dragon
|  |  | Skandi Gamma | Skandi Gamma | Energy Scout | MV Island Crusader | MV Island Crusader
|  |  | Skandi Kvitsøy | Skandi Kvitsøy | Havila Mercury | MV Island Contender | MV Island Contender
|  |  | Skandi Marøy | Skandi Marøy | Havila Mars | MV Island Condor | MV Island Condor
|  |  | Skandi Mongstad | Skandi Mongstad | Havila Venus | MV Island Commander | MV Island Commander
|  |  | Skandi Nova | Skandi Nova | Havila Jupiter | MV Island Clipper | MV Island Clipper
|  |  | Skandi Rona | Skandi Rona | Havila Neptune | MV Island Champion | MV Island Champion
|  |  | Skandi Sotra | Skandi Sotra | Havila Charisma | MV Island Chieftain | MV Island Chieftain
|  |  | Skandi Texel | Skandi Texel | Havila Borg | MV Island Challenger | MV Island Challenger
|  |  | Acergy Viking | Acergy Viking | Havila Foresight | MV Island Victory | MV Island Victory
|  |  | NS Orla | NS Orla | Havila Fortune | MV Island Vanguard | MV Island Vanguard
|  |  | FS Frayja | FS Frayja | Havila Crusader | MV Island Diligence | MV Island Diligence
|  |  | Viking Queen | Viking Queen | Havila Commander | MV Island Crown | MV Island Crown
|  |  | Subsea Viking | Subsea Viking | Havila Aurora | KL Brevikfjord | KL Brevikfjord
|  |  | Viking Athene | Viking Athene | Havila Fanø | KL Barentsfjord | KL Barentsfjord
|  |  | Viking Avant | Viking Avant | Havila Herøy | KL Brisfjord | KL Brisfjord
|  |  | Viking Energy | Viking Energy | Havila Clipper | KL Brofjord | KL Brofjord
|  |  | Viking Lady | Viking Lady | Havila Troll | KL Sandefjord | KL Sandefjord
|  |  | Viking Prince | Viking Prince | MV Island Defender | KL Saltfjord | KL Saltfjord
|  |  | Viking Princess | Viking Princess | MV Island Endeavour | Siddis Sailor | Siddis Sailor
|  |  | Christina E | Christina E | MV Island Empress | Siddis Mariner | Siddis Mariner
|  |  | Energy Duchess | Energy Duchess | MV Island Duchess | Normand Pioneer | Normand Pioneer
|  |  | Energy Empress | Energy Empress | MV Island Dragon | Olympic Orion | Olympic Orion
|  |  | Energy Swan | Energy Swan | MV Island Crusader | Olympic Taurus | Olympic Taurus
|  |  | Energy Scout | Energy Scout | MV Island Contender | Olympic Commander | Olympic Commander
|  |  | Havila Mercury | Havila Mercury | MV Island Condor | Olympic Electra | Olympic Electra
|  |  | Havila Mars | Havila Mars | MV Island Commander | Olympic Artemis | Olympic Artemis
|  |  | Havila Venus | Havila Venus | MV Island Clipper | Olympic Delta | Olympic Delta
|  |  | Havila Jupiter | Havila Jupiter | MV Island Champion | Olympic Hercules | Olympic Hercules
|  |  | Havila Neptune | Havila Neptune | MV Island Chieftain | Olympic Pegasus | Olympic Pegasus
|  |  | Havila Charisma | Havila Charisma | MV Island Challenger | Olympic Energy | Olympic Energy
|  |  | Havila Borg | Havila Borg | MV Island Victory | Olympic Promoter | Olympic Promoter
|  |  | Havila Foresight | Havila Foresight | MV Island Vanguard | Olympic Elena | Olympic Elena
|  |  | Havila Fortune | Havila Fortune | MV Island Diligence | Edda Ferd | Edda Ferd
|  |  | Havila Crusader | Havila Crusader | MV Island Crown | Edda Fram | Edda Fram
|  |  | Havila Commander | Havila Commander | KL Brevikfjord | Edda Frende | Edda Frende
|  |  | Havila Aurora | Havila Aurora | KL Barentsfjord | Edda Fjord | Edda Fjord
|  |  | Havila Fanø | Havila Fanø | KL Brisfjord | Edda Fides | Edda Fides
|  |  | Havila Herøy | Havila Herøy | KL Brofjord | Edda Mistral | Edda Mistral
|  |  | Havila Clipper | Havila Clipper | KL Sandefjord | Edda Passat | Edda Passat
|  |  | Havila Harmony | Havila Harmony | KL Saltfjord | Topaz Tiamat | Topaz Tiamat
|  |  | Havila Troll | Havila Troll | S/L Bintang | Rem Arctic | Rem Arctic
|  |  | MV Island Defender | MV Island Defender | Siddis Sailor | Rem Cetus | Rem Cetus
|  |  | MV Island Endeavour | MV Island Endeavour | Siddis Mariner | Rem Insula | Rem Insula
|  |  | MV Island Empress | MV Island Empress | Normand Pioneer | Rem Mira | Rem Mira
|  |  | MV Island Duchess | MV Island Duchess | Olympic Orion | Rem Mistral | Rem Mistral
|  |  | MV Island Dragon | MV Island Dragon | Olympic Taurus | Rem Supplier | Rem Supplier
|  |  | MV Island Crusader | MV Island Crusader | Olympic Commander | Rem Trader | Rem Trader
|  |  | MV Island Contender | MV Island Contender | Olympic Electra | Hemir Horizon | Hemir Horizon
|  |  | MV Island Condor | MV Island Condor | Olympic Artemis | Hermi Fighter | Hermi Fighter
|  |  | MV Island Commander | MV Island Commander | Olympic Delta | Hermit Storm | Hermit Storm
|  |  | MV Island Clipper | MV Island Clipper | Olympic Hercules | Hermit Galaxy | Hermit Galaxy
|  |  | MV Island Champion | MV Island Champion | Olympic Pegasus | Hermit Thunder | Hermit Thunder
|  |  | MV Island Chieftain | MV Island Chieftain | Olympic Energy | Hermit Power | Hermit Power
|  |  | MV Island Challenger | MV Island Challenger | Olympic Promoter | Hermit Guardian | Hermit Guardian
|  |  | MV Island Vanguard | MV Island Vanguard | Olympic Elena | Hermit Prosper | Hermit Prosper
|  |  | MV Island Valiant | MV Island Valiant | Edda Fauna | Rem Eir | Rem Eir
|  |  | MV Island Diligence | MV Island Diligence | Edda Flora | Rem Mist | Rem Mist
|  |  | MV Island Crown | MV Island Crown | Edda Ferd | Rem Hrist | Rem Hrist
|  |  | MV Ocean Intervention | MV Ocean Intervention | Edda Fram | Neptun Naiad | Neptun Naiad
|  |  | MV Island Centurion | MV Island Centurion | Edda Frende | H U Sverdrup II | H U Sverdrup II
|  |  | MV Island Captain | MV Island Captain | Edda Fjord | M/S Nautilus Survey | M/S Nautilus Survey
|  |  | KL Brevikfjord | KL Brevikfjord | Edda Fides | Siem Pilot | Siem Pilot
|  |  | KL Barentsfjord | KL Barentsfjord | Edda Mistral | Siem Hanne | Siem Hanne
|  |  | KL Brisfjord | KL Brisfjord | Edda Passat | Siem Symphony | Siem Symphony
|  |  | KL Brofjord | KL Brofjord | Topaz Tiamat | Siem Pride | Siem Pride
|  |  | KL Sandefjord | KL Sandefjord | Rem Arctic | Siem Thiima | Siem Thiima
|  |  | KL Saltfjord | KL Saltfjord | Rem Cetus | Siem N-Sea | Siem N-Sea
|  |  | Skagerak | Skagerak | Rem Insula | Siem Marlin | Siem Marlin
|  |  | Nexans Aurora | Nexans Aurora | Rem Mira | Siem Amethyst | Siem Amethyst
|  |  | Siddis Sailor | Siddis Sailor | Rem Mistral | Siem Opal | Siem Opal
|  |  | Siddis Mariner | Siddis Mariner | Rem Supplier | Siem Garnet | Siem Garnet
|  |  | Normand Flower | Normand Flower | Rem Trader | Siem Diamond | Siem Diamond
|  |  | Rockpiper | Rockpiper | Hemir Horizon | Siem Topaz | Siem Topaz
|  |  | Olympic Orion | Olympic Orion | Hermi Fighter | Siem Ruby | Siem Ruby
|  |  | Olympic Electra | Olympic Electra | Hermit Storm | Siem Aquamarine | Siem Aquamarine
|  |  | Olympic Artemis | Olympic Artemis | Hermit Galaxy | Siem Sapphire | Siem Sapphire
|  |  | Olympic Delta | Olympic Delta | Hermit Thunder | Siem Emerald | Siem Emerald
|  |  | Olympic Hercules | Olympic Hercules | Hermit Power | Siem Pearl | Siem Pearl
|  |  | Olympic Pegasus | Olympic Pegasus | Hermit Guardian | Stril Mar | Stril Mar
|  |  | Olympic Energy | Olympic Energy | Hermit Prosper | Stril Barents | Stril Barents
|  |  | Olympic Promoter | Olympic Promoter | Rem Eir | Stril Luna | Stril Luna
|  |  | Olympic Elena | Olympic Elena | Rem Mist | Stril Polar | Stril Polar
|  |  | Edda Fauna | Edda Fauna | Rem Hrist | Stril Orion | Stril Orion
|  |  | Edda Flora | Edda Flora | Neptun Naiad | Stril Mermaid | Stril Mermaid
|  |  | Edda Ferd | Edda Ferd | H U Sverdrup II | Stril Odin | Stril Odin
|  |  | Edda Fram | Edda Fram | M/S Nautilus | Strilmøy | Strilmøy
|  |  | Edda Frende | Edda Frende | M/S Nautilus Survey | Stril Pioner | Stril Pioner
|  |  | Edda Fauna | Edda Fauna | Siem Pilot | Stril Merkur | Stril Merkur
|  |  | Edda Flora | Edda Flora | Siem Hanne | Stril Herkules | Stril Herkules
|  |  | Edda Fjord | Edda Fjord | Siem Symphony | Stril Poseidon | Stril Poseidon
|  |  | Edda Sun | Edda Sun | Siem Pride | Stril Mariner | Stril Mariner
|  |  | Edda Fides | Edda Fides | Siem Thiima | Strilborg | Strilborg
|  |  | Edda Mistral | Edda Mistral | Siem N-Sea | Stril Server | Stril Server
|  |  | Edda Passat | Edda Passat | Siem Marlin | Stril Explorer | Stril Explorer
|  |  | Rem Andes | Rem Andes | Siem Amethyst | Far Scotia | Far Scotia
|  |  | Rem Arctic | Rem Arctic | Siem Opal | Normand Jarl | Normand Jarl
|  |  | Rem Aquarius | Rem Aquarius | Siem Garnet | Normand Pacific | Normand Pacific
|  |  | Rem Cetus | Rem Cetus | Siem Diamond | Far Superior | Far Superior
|  |  | Rem Insula | Rem Insula | Siem Topaz | Normand Fortress | Normand Fortress
|  |  | Rem Mira | Rem Mira | Siem Ruby | Nor Valiant | Nor Valiant
|  |  | Rem Mistral | Rem Mistral | Siem Aquamarine | Normand Drott | Normand Drott
|  |  | Rem Supplier | Rem Supplier | Siem Sapphire | Normand Ferking | Normand Ferking
|  |  | Rem Trader | Rem Trader | Siem Emerald | Normand Prosper | Normand Prosper
|  |  | Hemir Horizon | Hemir Horizon | Siem Pearl | Normand Ranger | Normand Ranger
|  |  | Hermi Fighter | Hermi Fighter | Stril Mar | Normand Scorpion | Normand Scorpion
|  |  | Hermit Storm | Hermit Storm | Stril Barents | Normand Sirius | Normand Sirius
|  |  | Hermit Galaxy | Hermit Galaxy | Stril Luna | Normand Topazio | Normand Topazio
|  |  | Hermit Thunder | Hermit Thunder | Stril Polar | Nor Captain | Nor Captain
|  |  | Hermit Power | Hermit Power | Stril Orion | Nor Spring | Nor Spring
|  |  | Hermit Guardian | Hermit Guardian | Stril Mermaid | BOS Turquesa | BOS Turquesa
|  |  | Hermit Prosper | Hermit Prosper | Stril Odin | BOS Turmalina | BOS Turmalina
|  |  | Rem Eir | Rem Eir | Strilmøy | Far Sapphire | Far Sapphire
|  |  | Rem Mist | Rem Mist | Stril Pioner | Normand Saracen | Normand Saracen
|  |  | Rem Hrist | Rem Hrist | Stril Merkur | Far Sagaris | Far Sagaris
|  |  | Neptun Naiad | Neptun Naiad | Stril Herkules | Far Scout | Far Scout
|  |  | H U Sverdrup II | H U Sverdrup II | Stril Poseidon | Far Statesman | Far Statesman
|  |  | C/V Fjordkabel | C/V Fjordkabel | Stril Mariner | Far Stream | Far Stream
|  |  | C/V Nordkabel | C/V Nordkabel | Strilborg | Far Sigma | Far Sigma
|  |  | M/S Nautilus | M/S Nautilus | Stril Server | Far Senator | Far Senator
|  |  | M/S Nautilus Survey | M/S Nautilus Survey | Stril Explorer | Far Sword | Far Sword
|  |  | M/S Nautilus Ocean | M/S Nautilus Ocean | "Målebåt" (19 fots buster med utstyr) | Far Santana | Far Santana
|  |  | T/B Nautilus Balder | T/B Nautilus Balder | Far Scotia | Normand Atlantic | Normand Atlantic
|  |  | Siem Pilot | Siem Pilot | Normand Jarl | Normand Borg | Normand Borg
|  |  | Siem Hanne | Siem Hanne | Normand Pacific | Normand Ivan | Normand Ivan
|  |  | Siem Symphony | Siem Symphony | Far Superior | Normand Mariner | Normand Mariner
|  |  | Siem Pride | Siem Pride | Normand Fortress | Normand Master | Normand Master
|  |  | Siem Thiima | Siem Thiima | Nor Valiant | Normand Neptun | Normand Neptun
|  |  | Siem N-Sea | Siem N-Sea | Normand Drott | Normand Titan | Normand Titan
|  |  | Siem Marlin | Siem Marlin | Normand Ferking | Far Sabre | Far Sabre
|  |  | Siem Amethyst | Siem Amethyst | Normand Prosper | Far Scimitar | Far Scimitar
|  |  | Siem Opal | Siem Opal | Normand Ranger | Far Sound | Far Sound
|  |  | Siem Garnet | Siem Garnet | Normand Scorpion | Far Sovereign | Far Sovereign
|  |  | Siem Diamond | Siem Diamond | Normand Sirius | Far Strait | Far Strait
|  |  | Siem Topaz | Siem Topaz | Normand Topazio | Lady Astrid | Lady Astrid
|  |  | Siem Ruby | Siem Ruby | Nor Captain | Nor Tigerfish | Nor Tigerfish
|  |  | Siem Aquamarine | Siem Aquamarine | Nor Spring | Lady Caroline | Lady Caroline
|  |  | Siem Sapphire | Siem Sapphire | BOS Turquesa | Sea Ocelot | Sea Ocelot
|  |  | Siem Emerald | Siem Emerald | BOS Turmalina | Sea Panther | Sea Panther
|  |  | Siem Pearl | Siem Pearl | Far Sapphire | Sea Tiger | Sea Tiger
|  |  | Big Orange | Big Orange | Normand Saracen | Elang Laut 1 | Elang Laut 1
|  |  | Stril Mar | Stril Mar | Far Sagaris | Normand Arctic | Normand Arctic
|  |  | Stril Barents | Stril Barents | Far Scout | Normand Aurora | Normand Aurora
|  |  | Stril Luna | Stril Luna | Far Statesman | Normand Carrier | Normand Carrier
|  |  | Stril Polar | Stril Polar | Far Stream | Normand Falnes | Normand Falnes
|  |  | Stril Orion | Stril Orion | Far Sigma | Normand Flipper | Normand Flipper
|  |  | Stril Mermaid | Stril Mermaid | Far Senator | Normand Fortune | Normand Fortune
|  |  | Stril Odin | Stril Odin | Far Sword | Normand Leader | Normand Leader
|  |  | Strilmøy | Strilmøy | Far Santana | Norman Serenade | Norman Serenade
|  |  | Stril Pioner | Stril Pioner | Normand Atlantic | Norman Server | Norman Server
|  |  | Stril Merkur | Stril Merkur | Normand Borg | Normand Service | Normand Service
|  |  | Stril Herkules | Stril Herkules | Normand Ivan | Normand Sitella | Normand Sitella
|  |  | Stril Poseidon | Stril Poseidon | Normand Mariner | Normand Skimmer | Normand Skimmer
|  |  | Stril Mariner | Stril Mariner | Normand Master | Normand Skipper | Normand Skipper
|  |  | Strilborg | Strilborg | Normand Neptun | Normand Springer | Normand Springer
|  |  | Stril Server | Stril Server | Normand Titan | Normand Starling | Normand Starling
|  |  | Stril Explorer | Stril Explorer | Far Sabre | Normand Sun | Normand Sun
|  |  | Far Scotia | Far Scotia | Far Scimitar | Normand Supporter | Normand Supporter
|  |  | Nor Valiant | Nor Valiant | Far Sound | Normand Supra | Normand Supra
|  |  | Normand Progress | Normand Progress | Far Sovereign | Normand Surfer | Normand Surfer
|  |  | Normand Baltic | Normand Baltic | Far Strait | Normand Swan | Normand Swan
|  |  | Normand Commander | Normand Commander | Lady Astrid | Normand Swift | Normand Swift
|  |  | Normand Mermaid | Normand Mermaid | Nor Tigerfish | Norman Sygna | Norman Sygna
|  |  | Normand Poseidon | Normand Poseidon | Lady Caroline | Normand Titus | Normand Titus
|  |  | Normand Australis | Normand Australis | Sea Ocelot | Norman Tortuga | Norman Tortuga
|  |  | Normand Tonjer | Normand Tonjer | Sea Panther | Normand Naley | Normand Naley
|  |  | Far Saga | Far Saga | Sea Tiger | Far Scotsman | Far Scotsman
|  |  | Normand Drott | Normand Drott | Elang Laut 1 | Far Searcher | Far Searcher
|  |  | Normand Ferking | Normand Ferking | Normand Arctic | Far Solitaire | Far Solitaire
|  |  | Normand Prosper | Normand Prosper | Normand Aurora | Far Seeker | Far Seeker
|  |  | Normand Ranger | Normand Ranger | Normand Carrier | Far Spica | Far Spica
|  |  | Normand Scorpion | Normand Scorpion | Normand Falnes | Far Swan | Far Swan
|  |  | Normand Sirius | Normand Sirius | Normand Flipper | Far Symphony | Far Symphony
|  |  | Normand Topazio | Normand Topazio | Normand Fortune | Sea Falcon | Sea Falcon
|  |  | Nor Captain | Nor Captain | Normand Leader | Sea Flyer | Sea Flyer
|  |  | Nor Spring | Nor Spring | Norman Serenade | Sea Forth | Sea Forth
|  |  | BOS Turquesa | BOS Turquesa | Norman Server | Sea Frost | Sea Frost
|  |  | BOS Turmalina | BOS Turmalina | Normand Service | Sea Spark | Sea Spark
|  |  | Far Sapphire | Far Sapphire | Normand Sitella | Sea Spear | Sea Spear
|  |  | Normand Saracen | Normand Saracen | Normand Skimmer | Sea Tantalus | Sea Tantalus
|  |  | Far Sagaris | Far Sagaris | Normand Skipper | Sea Brasil | Sea Brasil
|  |  | Far Scout | Far Scout | Normand Springer | Normand Corona | Normand Corona
|  |  | Far Statesman | Far Statesman | Normand Starling | Normand Provider | Normand Provider
|  |  | Far Stream | Far Stream | Normand Sun | Normand Sira | Normand Sira
|  |  | Far Sigma | Far Sigma | Normand Supporter | Normand Supplier | Normand Supplier
|  |  | Far Senator | Far Senator | Normand Supra | Normand Trym | Normand Trym
|  |  | Far Sword | Far Sword | Normand Surfer | Norman Vibran | Norman Vibran
|  |  | Far Santana | Far Santana | Normand Swan | Far Spirit | Far Spirit
|  |  | Normand Atlantic | Normand Atlantic | Normand Swift | Far Splendour | Far Splendour
|  |  | Normand Borg | Normand Borg | Norman Sygna | Far Strider | Far Strider
|  |  | Normand Ivan | Normand Ivan | Normand Titus | Sea Angler | Sea Angler
|  |  | Normand Mariner | Normand Mariner | Norman Tortuga | Sea Bass | Sea Bass
|  |  | Normand Master | Normand Master | Normand Naley | Sea Pollock | Sea Pollock
|  |  | Normand Neptun | Normand Neptun | Far Scotsman | Sea Triumph | Sea Triumph
|  |  | Normand Titan | Normand Titan | Far Searcher | Sea Turbot | Sea Turbot
|  |  | Far Sabre | Far Sabre | Far Solitaire | Sea Trout | Sea Trout
|  |  | Far Scimitar | Far Scimitar | Far Seeker | Sea Witch | Sea Witch
|  |  | Far Sound | Far Sound | Far Spica | Elektron | Elektron
|  |  | Far Sovereign | Far Sovereign | Far Swan | Seaway Aimery | Seaway Aimery
|  |  | Far Strait | Far Strait | Far Symphony | Seaway Moxie | Seaway Moxie
|  |  | Lady Astrid | Lady Astrid | Sea Falcon | Normand Oceanic | Normand Oceanic
|  |  | Nor Tigerfish | Nor Tigerfish | Sea Flyer | Juanita | Juanita
|  |  | Lady Caroline | Lady Caroline | Sea Forth | Evita II | Evita II
|  |  | Sea Ocelot | Sea Ocelot | Sea Frost | Tanux I | Tanux I
|  |  | Sea Panther | Sea Panther | Sea Spark | Tanux II | Tanux II
|  |  | Sea Tiger | Sea Tiger | Sea Spear | Tanux III | Tanux III
|  |  | Elang Laut 1 | Elang Laut 1 | Sea Tantalus | Evita II | Evita II
|  |  | Normand Arctic | Normand Arctic | Sea Brasil | Ocean Europe | Ocean Europe
|  |  | Normand Aurora | Normand Aurora | Normand Corona | Vestland Cygnus | Vestland Cygnus
|  |  | Normand Carrier | Normand Carrier | Normand Provider | Norside Supporter | Norside Supporter
|  |  | Normand Falnes | Normand Falnes | Normand Sira | Norsea Fighter | Norsea Fighter
|  |  | Normand Flipper | Normand Flipper | Normand Supplier | Ocean Duke | Ocean Duke
|  |  | Normand Fortune | Normand Fortune | Normand Trym | Magne Viking | Magne Viking
|  |  | Normand Leader | Normand Leader | Norman Vibran | Njord Viking | Njord Viking
|  |  | Norman Serenade | Norman Serenade | Far Spirit | Loke Viking | Loke Viking
|  |  | Norman Server | Norman Server | Far Splendour | Brage Viking | Brage Viking
|  |  | Normand Service | Normand Service | Far Strider | Coey Viking | Coey Viking
|  |  | Normand Sitella | Normand Sitella | Sea Angler | Cooper Viking | Cooper Viking
|  |  | Normand Skimmer | Normand Skimmer | Sea Bass
|  |  | Normand Skipper | Normand Skipper | Sea Pollock
|  |  | Normand Springer | Normand Springer | Sea Triumph
|  |  | Normand Starling | Normand Starling | Sea Turbot
|  |  | Normand Sun | Normand Sun | Sea Trout
|  |  | Normand Supporter | Normand Supporter | Sea Witch
|  |  | Normand Supra | Normand Supra | Elektron
|  |  | Normand Surfer | Normand Surfer | Seaway Aimery
|  |  | Normand Swan | Normand Swan | Seaway Moxie
|  |  | Normand Swift | Normand Swift | Normand Oceanic
|  |  | Norman Sygna | Norman Sygna | Juanita
|  |  | Normand Titus | Normand Titus | Evita II
|  |  | Norman Tortuga | Norman Tortuga | Tanux I
|  |  | Normand Naley | Normand Naley | Tanux II
|  |  | Far Scotsman | Far Scotsman | Tanux III
|  |  | Far Searcher | Far Searcher | Evita II
|  |  | Far Solitaire | Far Solitaire | Ocean Europe
|  |  | Far Seeker | Far Seeker | Vestland Cygnus
|  |  | Far Spica | Far Spica | Norside Supporter
|  |  | Far Swan | Far Swan | Norsea Fighter
|  |  | Far Symphony | Far Symphony | Ocean Duke
|  |  | Sea Falcon | Sea Falcon | Magne Viking
|  |  | Sea Flyer | Sea Flyer | Njord Viking
|  |  | Sea Forth | Sea Forth | Loke Viking
|  |  | Sea Frost | Sea Frost | Brage Viking
|  |  | Sea Spark | Sea Spark | Coey Viking
|  |  | Sea Spear | Sea Spear | Cooper Viking
|  |  | Sea Tantalus | Sea Tantalus
|  |  | Sea Brasil | Sea Brasil
|  |  | Normand Corona | Normand Corona
|  |  | Normand Provider | Normand Provider
|  |  | Normand Sira | Normand Sira
|  |  | Normand Supplier | Normand Supplier
|  |  | Normand Trym | Normand Trym
|  |  | Norman Vibran | Norman Vibran
|  |  | Far Spirit | Far Spirit
|  |  | Far Splendour | Far Splendour
|  |  | Far Strider | Far Strider
|  |  | Sea Angler | Sea Angler
|  |  | Sea Bass | Sea Bass
|  |  | Sea Pollock | Sea Pollock
|  |  | Sea Triumph | Sea Triumph
|  |  | Sea Turbot | Sea Turbot
|  |  | Sea Trout | Sea Trout
|  |  | Sea Witch | Sea Witch
|  |  | Elektron | Elektron
|  |  | Seaway Aimery | Seaway Aimery
|  |  | Seaway Moxie | Seaway Moxie
|  |  | Seven Cruzeiro | Seven Cruzeiro
|  |  | Seven Navica | Seven Navica
|  |  | Seven Rio | Seven Rio
|  |  | Seven Seas | Seven Seas
|  |  | Seven Sun | Seven Sun
|  |  | Juanita | Juanita
|  |  | Evita II | Evita II
|  |  | Geo Barents | Geo Barents
|  |  | Tanux I | Tanux I
|  |  | Tanux II | Tanux II
|  |  | Tanux III | Tanux III
|  |  | Evita II | Evita II
|  |  | Ocean Europe | Ocean Europe
|  |  | Vestland Artemis | Vestland Artemis
|  |  | Vestland Cygnus | Vestland Cygnus
|  |  | Ocean Fortune | Ocean Fortune
|  |  | Solvik Supplier | Solvik Supplier
|  |  | Norside Supporter | Norside Supporter
|  |  | Ocean Mermaid | Ocean Mermaid
|  |  | Norsea Fighter | Norsea Fighter
|  |  | Ocean Pearl | Ocean Pearl
|  |  | Nordic Explorer | Nordic Explorer
|  |  | Ocean Sea | Ocean Sea
|  |  | Oceanic Champion | Oceanic Champion
|  |  | Ocean Duke | Ocean Duke
|  |  | Magne Viking | Magne Viking
|  |  | Njord Viking | Njord Viking
|  |  | Loke Viking | Loke Viking
|  |  | Brage Viking | Brage Viking
|  |  | Coey Viking | Coey Viking
|  |  | Cooper Viking | Cooper Viking
|  |  | Geo Caspian | Geo Caspian
|  |  | Oceanic Endeavour | Oceanic Endeavour
|  |  | Geco Bluefin | Geco Bluefin
|  | Environmental survey | Resource/metocean survey: buoy and sensor installation and operation Floting metmast installation? | Resource/metocean survey: buoy and sensors installation | Resource/metocean survey: Sensor operation and maintenance | Geophysical/Geotechnical and hydrographical survey | Geotechnical survey
Vessels with track record | # | 1 | 1 | 1 | 9 | 15 | 15
Capable vessels | # | 41 | 383 | 383 | 328 | 301 | 301
Vessel type value potential per GW | MNOK | 43.3188 | 19.2528 |  |  | 65.7002
[7 empty] | NOK/£ | 12.033
Dayrate- based est
Catapult
[7 empty] | k£-low | k£-high | days | M£/GW | MNOK | MNOK
|  | P1 | Sum of Development and consenting services | Vessel type | [5 empty] | 7.15 |  | 128.2718
|  | P2 | Sum env surveys | [6 empty] | 2.85 | 0 | 43.3188
|  | 2.1 | Benthic env.survey | Larger survey vsl |  |  | 5 | 10 | 90 | 0.45 | 0 | 10.8297
|  | 2.2 | Fish and shellfish surveys | Larger survey vsl |  |  | 5 | 10 | 90 | 0.4 | 0 | 10.8297
|  | 2.3 | Ornitological | Larger survey vsl |  |  | 5 | 10 | 90 | 1 | 0 | 10.8297
|  | 2.4 | Marine mammal | Larger survey vsl |  |  | 5 | 10 | 90 | 1 | 0 | 10.8297
|  | P3 | Sum resource and metocean assessment | [8 empty] | 19.2528
|  |  | Installation of metocean monitoring equipment/sensors | OCV |  |  | 38 | 50 | 20 | 1 |  | 12.033
|  | P3.3 | Maintenance of metocean systems | PSV |  |  | 10 | 20 | 30 | 0.3 | 0 | 7.2198 | 3 year x 10 days
|  | P4 | Sum geological surveys |  | 0 |  |  |  |  | 4 | 0 | 65.7002
|  | P4.1 | Geophysical surveys (incl. Operators) | Geo survey vsl |  |  | 19 | 26 | 60 | 0.7 | 0 | 18.7715
|  | P4.2 | Geotechnical surveys | Geo survey vsl |  |  | 19 | 26 | 90 | 2.5 | 0 | 28.1572
|  | P4.3 | Hydrographic surveys | Geo survey vsl |  |  | 19 | 26 | 60 | 0.8 | 0 | 18.7715
[11 empty] | 0 | 0
|  |  | Total Marine operations | [6 empty] | 8.15 | 0

## 2.Project logistics
Logistics for the consruction of the OWF
Main task |  | Heavy transport | Heavy transport | Heavy transport
Activity description |  | Transport of heavy and lage/long components from manufacturer to Onshore construction base port | Transport of heavy (large and high) components from manufacturer to Onshore construction base port | Transport of heavy (sensitive) components from manufacturer to Onshore construction base port
Vessel |  | Heavy transport vessel | Heavy transport vessel | RoRo vessel
|  | Blade transport | Jacket foundation transport | Nacelle transport
Vessel main characteristics |  | Large deck area and deck strength and loading capacity |  | Protected cargo space with power supply
Critical vessel equipment/technology |  | Deck loading capacity XXmt "Norwegian harbours max limit"<Beam< XXm "Norwegian harbours max limit"<Fully laden draught<YYm | Deck loading capacity XXmt "Norwegian harbours max limit"<Beam< XXm "Norwegian harbours max limit"<Fully laden draught<YYm | Deck loading capacity XXmt "Norwegian harbours max limit"<Beam< XXm "Norwegian harbours max limit"<Fully laden draught<Yym. Substantial power supply (50 hz and 60 Hz) to components for rotation of shafts and gears and to provide heating.
Norwegian suppliers |  | UWL (50% Fred. Olsen Ocean)
Market share
Trend/Opportunities |  | RoRo operations performed by converted/reinforced RoRo tonnage
Nor Market potential
Sub-task/Equipment
filters in the vessel list activated |  | Track records of vessels used towrds the wind industry. | Track records of vessels used towrds the wind industry. | Track records of vessels used towrds the wind industry.
Vessels - having been involved in wind project |  | Albatross | Albatross | MV Peak Belfast
|  | Hawk | Hawk | MV Peak Bergen
|  | Osprey | Osprey | MV Peak Bilbao
|  | MV Peak Belfast | MV Vestvind | MV Peak Bordeaux
|  | MV Peak Bergen | MV Boldwind | MV Peak Bremen
|  | MV Peak Bilbao |  | MV Peak Breskens
|  | MV Peak Bordeaux |  | MV Vestvind
|  | MV Peak Bremen |  | MV Boldwind
MV Peak Breskens
MV Vestvind
MV Boldwind
filters in the vessel list activated |  | Barges (tugs not included), Walleinus wilhelmsen vessels | Barges (tugs not included), Walleinus wilhelmsen vessels | Barges (tugs not included), Walleinus wilhelmsen vessels
Vessels - capable of doing jobs (include RoRo, roPax, bulk ++) |  | Tronds Barge 33 | Tronds Barge 33 | Tronds Barge 33
|  | Tronds Barge 30 | Tronds Barge 30 | Tronds Barge 30
|  | Tronds Barge 28 | Tronds Barge 28 | Tronds Barge 28
|  | Tronds Barge 132 | Tronds Barge 132 | Tronds Barge 132
|  | Tronds Barge 131 | Tronds Barge 131 | Tronds Barge 131
|  | Tronds Barge 45 | Tronds Barge 45 | Tronds Barge 45
|  | Tronds Barge 42 | Tronds Barge 42 | Tronds Barge 42
|  | Tronds Barge 37 | Tronds Barge 37 | Tronds Barge 37
|  | Tronds Barge 32 | Tronds Barge 32 | Tronds Barge 32
|  | Tronds Barge 29 | Tronds Barge 29 | Tronds Barge 29
|  | UR 5 | UR 5 | UR 5
|  | UR 7 | UR 7 | UR 7
|  | UR 8 | UR 8 | UR 8
|  | UR 93 | UR 93 | UR 93
|  | UR 95 | UR 95 | UR 95
|  | UR 96 | UR 96 | UR 96
|  | UR 97 | UR 97 | UR 97
|  | UR 98 | UR 98 | UR 98
|  | UR 99 | UR 99 | UR 99
|  | UR 141 | UR 141 | UR 141
|  | UR 171 | UR 171 | UR 171
|  | UR 901 | UR 901 | UR 901
|  | UR 902 | UR 902 | UR 902
|  | Heavy transport - blades | Heavy transport - towers/foundations/TP | Heavy transport - nacelles
Vessels with track record | # | 12 | 6 | 9
Capable vessels | # | 35 | 29 | 32
Vessel type value potential per GW | MNOK | 23.0633 | 65.3459 | 6.0165
[6 empty] | NOK/£ | 12.033
LCC Day rate based
|  |  |  | day rate k£ | day rate kUSD | units | units/voyage | voyages | days /voyage | k£ | MNOK(£)
|  | Foundations | Heavy trnspt | 23 | 35 | 66.6667 | 3 | 22.2222 | 5 | 2555.5556 | 30.751
|  | TP | Heavy trnspt | 23 | 35 | 66.6667 | 8 | 8.3333 | 5 | 958.3333 | 11.5316
|  | Blades | Heavy trnspt | 23 | 35 | 200 | 12 | 16.6667 | 5 | 1916.6667 | 23.0633
|  | Towers | Heavy trnspt | 23 | 35 | 66.6667 | 4 | 16.6667 | 5 | 1916.6667 | 23.0633
|  | Nacelles | RoRo | 15 | 20 | 66.6667 | 10 | 6.6667 | 5 | 500 | 6.0165
94.4256

## FWT construction
[11 empty] | Foundation positioning in construction harbour | WTG construction (in harbour)
|  | Main task |  | FWT positioning | Mooring prelay/hook-up | FWT construction (Crane vessel) | Securing site | Construction barge
|  |  |  | Positioning and maintaining in position foundation |  | Lifting WTG(including tower, nacelle and balde) onto foundation,
|  |  |  | Tug: 5000-7000 £ | AHTS: 8000-30.000 £
|  |  |  | Tug boats | AHTS | Crane vessel, shearleg crane - unless performed by land-based crane
Large deck for the handling of boyancy/coupling elements. Bollard pull, Tug winches, towing pins, shark-jaw
|  |  |  | Tug winches, DP-2, Bollard pull 100 mt | Tug winches 450t og 500t DP-2, Bollard pull 300 mt
Eide. Changed name to Tronds Marine
|  |  |  | track record |  | track record
|  |  |  | No track record of this, except the french VB Croisic and VB Ouragan | No track record showing this | No track record showing this
|  |  |  | Tugs bp>100mt. 100mt is really high, when supporting rigs, typically around 60 mt is used |  | Same as for fixed: DP-2, Crane capacity>1200 mt; Lift height >150 m above deck; minimum radius< XXm Jacking system operability 2.5 m Hs; Spud cans
|  |  |  | Audax | Tug winches 450t og 500t DP-2, Bollard pull 300 mt | Brave Tern
|  |  |  | Dux | Skandi Hercules | Seaway Yudin ??
|  |  |  | Pax | Skandi Skansen | Seaway Strashnov ??
[5 empty] | Skandi Amazonas | Alfa Lift (newbuild 2021)
[5 empty] | Skandi Iceman | Vind 1 (newbuild)
[5 empty] | Skandi Iguacu | Vind 2 (newbuild)
[5 empty] | Skandi Vega | BT-220IU (newbuild)
[5 empty] | MV Island Victory | Bold Tern
KL Sandefjord
KL Saltfjord
Normand Installer
Siem Topaz
Siem Ruby
Siem Sapphire
Normand Drott
Normand Prosper
|  |  |  | FWT positioning (Tug) | Mooring prelay/hook-up (AHTS) | FWT construction (Crane vessel) | Securing site (guard vsl) | Construction barge
0 | Vessels with track record | # |  | 0 | 0 | 0
| Capable vessels | # |  | 13 | 16 | 8 | 0
| Vessel type value potential per GW right hand scale | MNOK |  | 22.4616 | 51.0199 | 320.88 | 65.8807 | 48.132
[6 empty] | #WTG | 66.6667
[6 empty] | NOK/£ | 12.033
|  |  | day rate £ |  |  |  |  | Day rate based
|  |  | low | high | vsl units | days | k£ | MNOK
| Foundation positioning during construction | Tug | 5 | 7 | 2 | 133.3333 | 933.3333 | 22.4616
| Mooring system pre-lay | AHTS | 8 | 30 | 1 | 8 | 240 | 2.8879 | 2 | days/found 4 instances (4 parallel construction)
| Mooring system hook-up | AHTS | 8 | 30 | 1 | 133.3333 | 4000 | 48.132 | 2 | days/found incl. WoW (1.5m/s Hs)
| Construction barge | Barge | 3 | 5 | 2 | 133.3333 | 666.6667 | 16.044 | 2 | days/found
| Securing site (harbour) | Guard vsl | 5 | 15 | 1 | 365 | 5475 | 65.8807
| Foundation/FWT positioning during construction | Tug | 5 | 7 | 2 | 133.3333 | 933.3333 | 22.4616
| FWT construction | FIV | 150 | 200 | 1 | 133.3333 | 26666.6667 | 320.88 | 2 | days per FWT
498.7478
[11 empty] | Foundation positioning in construction harbour | WTG construction (in harbour)
[11 empty] | 0 | 0
[11 empty] | 1 | 1

## 3.Cable laying and associated
Cable laying
Cable laying from shore to OSS (export) and between the WTGs and the OSS (inter-array cable). Offshore cable installation (export and array cables) involves the following activities:  Cable lay  Cable burial  Cable pull-in (to turbine, substation or shore), and  Electrical testing and termination.
Main task |  | Array cable lay | Export cable lay | Cable burial | Rock installation/dumping | Trenching | Pull-in
Activity description |  | Pre -trenching (with plough) and cable laying. Tools such as ROV for pre-trenching, vertical injector jetting sled are also possible to use while less common. Burial may be performed in the same process (along with the laying). Installation of dynamic cables including boyancy modules. | Pre -trenching and cable laying. Installation of dynamic cables including boyancy modules. | Burial may normally be left to the powers of nature (currents). Otherwise a cable burial vessel performs the burial with a trenching ROV, vertical injector (fluidising the sediment) or a jetting sled. | Insufficient burial or cable exposure is typically resolved by remedial measures including protective mattressing and rock dumping,
Vessel |  | Cable layer /Offshore Construction Vessel | Large cable layer (CLV) |  | Rock dumping vessel
Vessel main characteristics |  | Manoeuvering capabilities, large deck space/loading capacity for split carousel and CPS. DP class | Manoeuvering capabilities, large deck space/loading capacity for carousel and CPS. Deck crane for handling of cable tools. DP class | A-frame /Deck crane for postioning of ploughs/trench cutting machines and ROV | A DP class fall pipe vessel, or (occasionally) side-dumping vessels. Provided with reinforced deck and compartements for loading and transport of the rocks.Fall pipe vessel rock offloading system includes excavators, conveyor belts, hoppers, rock weighing system,fallpipe and fallpipe tower ( for storage, launch and recovery of fall pipe). Horizontal installation accuracy is less than 1 m, vertical accuracy in order of +/- 20 cm (dependning on rock size)
Critical vessel equipment/technology |  | DP-2, (break-back) tensioners , ROV hangar. 2-3-4 split carousel. A-frame /Deck crane for postioning of ploughs/trench cutting machines and work-class ROV and quadrant deployment frame. Operability in 3m Hs | DP-2, dedicated quadrant deployment frame , multiple (break-back) tensioners , ROV hangar Large (5-10.000 mt) carousel. A-frame /Deck crane for postioning of ploughs/trench cutting machines and work-class ROV. Operability in 3m Hs | None governing the vessel dimensjons or design apart from crane being able to launch and recover the plough, injector or jetting sled and work-class ROV. | DP-2; ROV hangar
Intl suppliers |  | Boskalis, Global Marine and Subsea 7, VanOrd(Nexus), JdN, Nexans, DEME, NKT | Boskalis, Global Marine and Subsea 7, VanOrd(Nexus), JdN, DEME |  | Boskalis, Peter Madsen Rederi, Tideway (DEME Group) and Van Oord Offshore Wind.
Norwegian suppliers |  | Deep Ocean, Solstad, Global Offshore, Siem, Nexans, Ocean Yield, Fugro | Nexans Norway (Aurora, for Nexans cables), Ocean Installer
Market share
Trend/Opportunities |  | For work in ultra deepwater, the deck to be prepared to accommodate a vertical lay tower to enable sufficient high tension hold-back capabilities. Larger turbines implies larger distances between the turbines which again leads to larger quantaties of inter-array cabling and more associated cable laying work. Hence increased need of capacity is expected. The increased turbine sizes also implies larger (thicker/heavier) calbing wich also drives the capacity requirement. | Increased specialisation. Cable supplier provide their specialized , large capacity vessels for export cable laying only. To enable complete cable-lay capabilities ranging from the deepwater to the shore vessel to be beachable in fully laden condition. Fitted with a six-point mooring system. For work in ultra deepwater, the deck to be prepared to accommodate a vertical lay tower to enable sufficient high tension hold-back capabilities. Export cable laying capacity is expected to be satisfied.
Nor Market potential
Sub-task/Equipment |  |  |  |  | Equipped with fallpipe ROV and survey ROV
Trenching/Burial |  | by ROV or plough. Separate pre-activity/separate vessel or performed by cable layer combined with laying
Burial |  | plough/vertical injector/jetting sled. Separate post lay-activity and vessel or combined with laying
Canyon Offshore (Helix ES), Global Marine and Van Oord Offshore Wind.
Pull-in |  | Crane/A-frame/quadrant deployment frame. Normally combined with laying of array cables | Crane/quadrant deplyoment frame. Separate or combined with laying for expoert cables
The Normand Clipper will be able to install fiber-optic cables using two 12-metric ton linear cable engines, jointing and testing capability, a cable plough, trenching system and work-class ROVs for post-lay inspectio
he Normand Clipper is currently being fitted with a 4,000-metric ton cable carousel, two 15-metric ton cable tensioners, a 25-metric ton quadrant deployment frame, and an integrated control system. It will also be capable of operating in a significant wave height up to 3.0 m (9.8 ft).
nstalling up to three inter array cables per day
filters in the vessel list activated |  | Track record: Note that the Siem vessels are not confirmed by Siem. | Track record: | Track record: | Track record:
Vessels - having been involved in wind project |  | C/V Fjordkabel | Skagerak | Edda Freya | Tronds Barge 132
|  | Connector |  | Volantis | Tronds Barge 131
|  | Edda Flora | Elektron | Havila Phoenix | Tronds Barge 45
|  | Edda Freya | Edda Freya | Ocean Challenger | Tronds Barge 42
|  | Elektron |  | Skandi Neptune | Connector
|  | Havila Jupiter |  |  | Rockpiper
Larissa
Normand Clipper
Normand Vision
Olympic Ares
Olympic Artemis
Olympic Challenger
Olympic Commander
Olympic Delta
Olympic Intervention IV
Olympic Taurus
Olympic Triton
Olympic Zeus
Polar King
Polar Prince
Rem Inspector
Rem Saltire
Seaway Aimery
Siem Barracuda
Siem Day
Siem Spearfish
Siem Stingray
Volantis
filters in the vessel list activated |  | Included: offshore construction with potential A-frame. Flex lay, rigid lay: Must have ROV or support vessel with ROV. Must have deck size above 1400m3. Rigid lay can perform with small modifications. Not: PSVs, | The same vessels are used as for array in addition to the ones that has track record for array. In practice, they are not likely to be used, because export cable laying requires more specialized vessels, such as Nexans Aurora. Included: offshore construction with potential A-frame. Flex lay, rigid lay: Must have ROV or support vessel with ROV. Must have deck size above 1400m3. Rigid lay can perform with small modifications. Lariss have only done export cable survey, Not included: PSVs | Vessels with a-frame, ROV, and deck size above 500m2 for burial equipment are included, potential A-frame. Not included: PSVs | Rock dumping can also be done by dumping bags with cranes, thus I have included vessels with crane larger than 50 ton and deck larger than 500m2, and ROV, and min DP2. However, it is unlikely that expensive construction subsea vessels will in practice be used due to price
Vessels - capable of doing jobs
|  | BOA Sub C | BOA Sub C | Volantis | Volantis | BOA Sub C
|  | Deep Cygnus | C/V Fjordkabel | Skandi Acergy | Skandi Acergy | C/V Fjordkabel
|  | Grand Canyon | Connector | Skandi Africa | Skandi Africa | Connector
|  | Grand Canyon II | Deep Cygnus | Skandi Hawk | Skandi Hawk | Deep Cygnus
|  | Grand Canyon III | Edda Flora | Skandi Hercules | Skandi Neptune | Edda Flora
|  | Havila Phoenix | Grand Canyon | Skandi Neptune | Skandi Niteroi | Grand Canyon
|  | Nexans Aurora | Grand Canyon II | Skandi Niteroi | Skandi Olinda | Grand Canyon II
|  | Normand Cutter | Grand Canyon III | Skandi Olinda | Skandi Patagonia | Grand Canyon III
|  | Normand Frontier | Havila Jupiter | Skandi Patagonia | Skandi Recife | Havila Jupiter
|  | Normand Jarstein | Havila Phoenix | Skandi Recife | Skandi Salvador | Havila Phoenix
|  | Normand Maximus | Larissa | Skandi Salvador | Skandi Seven | Larissa
|  | Normand Navigator | Nexans Aurora (not yet delivered) | Skandi Seven | Skandi Singapore | Nexans Aurora (not yet delivered)
|  | Normand Oceanic | Normand Clipper | Skandi Singapore | Skandi Skansen | Normand Clipper
|  | Normand Pioneer | Normand Cutter | Skandi Skansen | Skandi Vinland | Normand Cutter
|  | Normand Sentinel | Normand Frontier | Skandi Vinland | Skandi Vitoria | Normand Frontier
|  | Normand Vision | Normand Jarstein | Skandi Hera | Skandi Hera | Normand Jarstein
|  | Polar Onyx | Normand Maximus | Skandi Iceman | Viking Neptun | Normand Maximus
|  | Polar Prince | Normand Navigator | Skandi Paraty | Acergy Viking | Normand Navigator
|  | Seven Arctic | Normand Oceanic | Skandi Vega | Seven Viking | Normand Oceanic
|  | Seven Borealis | Normand Pioneer | Viking Neptun | Subsea Viking | Normand Pioneer
|  | Seven Cruzeiro | Normand Sentinel | Acergy Viking | Polar Queen | Normand Sentinel
|  | Seven Eagle | Normand Vision | Seven Viking | Larissa | Normand Vision
|  | Seven Pacific | Olympic Ares | Subsea Viking | Despina | Olympic Ares
|  | Seven Rio | Olympic Artemis | Polar Queen | Havila Phoenix | Olympic Artemis
|  | Seven Seas | Olympic Challenger | Energy Duchess | Havila Harmony | Olympic Challenger
|  | Seven Sun | Olympic Commander | Energy Empress | Havila Subsea | Olympic Commander
|  | Seven Waves | Olympic Delta | Larissa | MV Island Victory | Olympic Delta
|  | Skagerak | Olympic Intervention IV | Despina | MV Island Valiant | Olympic Intervention IV
|  | Skandi Acergy | Olympic Taurus | Havila Phoenix | MOU Island Frontier | Olympic Taurus
|  | Skandi Acu | Olympic Triton | Havila Mercury | MOU Island Constructor | Olympic Triton
|  | Skandi Africa | Olympic Zeus | Havila Mars | MOU Island Wellserver | Olympic Zeus
|  | Skandi Buzios | Polar King | Havila Venus | MV Ocean Intervention | Polar King
|  | Skandi Constructor | Polar Onyx | Havila Jupiter | MV Island Pride | Polar Onyx
|  | Skandi Neptune | Polar Prince | Havila Harmony | Normand Clipper | Polar Prince
|  | Skandi Niteroi | Rem Inspector | Havila Subsea | Normand Installer | Rem Inspector
|  | Skandi Olinda | Rem Saltire | MV Island Victory | Normand Flower | Rem Saltire
|  | Skandi Recife | Seaway Aimery | MV Island Vanguard | BOA Sub C | Seaway Aimery
|  | Skandi Vitoria | Seven Arctic | MV Island Valiant | Polar King | Seven Arctic
|  | Subsea Viking | Seven Borealis | MOU Island Frontier | Polar Prince | Seven Borealis
|  | Viking Neptun | Seven Cruzeiro | MOU Island Constructor | Deep Cygnus | Seven Cruzeiro
|  | SoCJe2sn | Seven Eagle | MOU Island Wellserver | Grand Canyon | Seven Eagle
|  | NKT Victoria | Seven Pacific | MV Ocean Intervention | Connector | Seven Pacific
|  | NORTH SEA ATLANTIC | Seven Rio | MV Island Pride | Olympic Orion | Seven Rio
|  | NORTH SEA GIANT | Seven Seas | KL Sandefjord | Olympic Zeus | Seven Seas
|  | Seven Mar | Seven Sun | KL Saltfjord | Olympic Taurus | Seven Sun
|  |  | Seven Waves | Skagerak | Olympic Commander | Seven Waves
|  |  | Siem Barracuda | Nexans Aurora | Olympic Triton | Siem Barracuda
|  |  | Siem Day | Normand Clipper | Olympic Intervention IV | Siem Day
|  |  | Siem Spearfish | Normand Installer | Olympic Ares | Siem Spearfish
|  |  | Siem Stingray | Normand Flower | Olympic Challenger | Siem Stingray
|  |  | Skagerak | BOA Sub C | Olympic Artemis | Skagerak
|  |  | Skandi Acergy | Polar King | Olympic Delta | Skandi Acergy
|  |  | Skandi Acu | Polar Prince | Edda Fauna | Skandi Acu
|  |  | Skandi Africa | Deep Cygnus | Edda Flora | Skandi Africa
|  |  | Skandi Buzios | Grand Canyon | Edda Fjord | Skandi Buzios
|  |  | Skandi Constructor | Connector | Edda Freya | Skandi Constructor
|  |  | Skandi Neptune | Olympic Orion | Edda Sun | Skandi Neptune
|  |  | Skandi Niteroi | Olympic Zeus | Rem Saltire | Skandi Niteroi
|  |  | Skandi Olinda | Olympic Taurus | Siem N-Sea | Skandi Olinda
|  |  | Skandi Recife | Olympic Commander | Siem Marlin | Skandi Recife
|  |  | Skandi Vitoria | Olympic Triton | Siem Day | Skandi Vitoria
|  |  | Subsea Viking | Olympic Intervention IV | Siem Barracuda | Subsea Viking
|  |  | Viking Neptun | Olympic Ares | Siem Spearfish | Viking Neptun
|  |  | Volantis | Olympic Challenger | Siem Stingray | Volantis
|  |  | SoCJe2sn | Olympic Artemis | Siem Helix 1 | SoCJe2sn
|  |  | NKT Victoria | Olympic Delta | Siem Helix 2 | NKT Victoria
|  |  | NORTH SEA ATLANTIC | Edda Fauna | Normand Jarstein | NORTH SEA ATLANTIC
|  |  | NORTH SEA GIANT | Edda Flora | Normand Pacific | NORTH SEA GIANT
|  |  | Seven Mar | Edda Fjord | Far Superior | Seven Mar
|  |  |  | Edda Freya | Normand Maximus
|  |  |  | Edda Sun | Normand Vision
|  |  |  | Rem Inspector | Normand Navigator
|  |  |  | Rem Saltire | Normand Sentinel
|  |  |  | Siem N-Sea | Normand Cutter
|  |  |  | Siem Marlin | Normand Frontier
|  |  |  | Siem Day | Normand Subsea
|  |  |  | Siem Barracuda | Normand Baltic
|  |  |  | Siem Spearfish | Normand Mermaid
|  |  |  | Siem Stingray | Normand Australis
|  |  |  | Siem Amethyst | Far Saga
|  |  |  | Siem Opal | Seven Arctic
|  |  |  | Siem Garnet | Seven Atlantic
|  |  |  | Siem Diamond | Seven Borealis
|  |  |  | Siem Topaz | Seven Cruzeiro
|  |  |  | Siem Ruby | Seven Eagle
|  |  |  | Siem Aquamarine | Seven Falcon
|  |  |  | Siem Sapphire | Seven Inagha
|  |  |  | Siem Emerald | Seven Kestrel
|  |  |  | Siem Pearl | Seven Oceans
|  |  |  | Siem Helix 1 | Seven Pacific
|  |  |  | Siem Helix 2 | Seven Pegasus
|  |  |  | Normand Jarstein | Seven Rio
|  |  |  | Normand Pacific | Seven Seas
|  |  |  | Far Superior | Seven Sun
|  |  |  | Normand Maximus | Seven Viking
|  |  |  | Normand Vision | Seven Waves
|  |  |  | Normand Navigator | Grant Candies
|  |  |  | Normand Sentinel | Harvey Intervention
|  |  |  | Normand Cutter | MMA Pinnacle
|  |  |  | Normand Frontier | Seven Vega
|  |  |  | Normand Subsea | Normand Oceanic
|  |  |  | Normand Baltic | Normand Subsea
|  |  |  | Normand Mermaid | Simar Esperanca
|  |  |  | Normand Australis | Grand Canyon II
|  |  |  | Far Saga | Grand Canyon III
|  |  |  | Normand Drott | SoCJe2sn
|  |  |  | Normand Ferking | NKT Victoria
|  |  |  | Normand Prosper | NORTH SEA ATLANTIC
|  |  |  | Normand Scorpion | NORTH SEA GIANT
|  |  |  | Far Sapphire | Seven Mar
Normand Saracen
Far Sagaris
Far Scout
Far Statesman
Elektron
Seaway Aimery
Seven Arctic
Seven Atlantic
Seven Borealis
Seven Cruzeiro
Seven Eagle
Seven Falcon
Seven Inagha
Seven Kestrel
Seven Oceans
Seven Pacific
Seven Pegasus
Seven Rio
Seven Seas
Seven Sun
Seven Viking
Seven Waves
Grant Candies
Harvey Intervention
MMA Pinnacle
Seven Vega
Normand Oceanic
Normand Subsea
Simar Esperanca
Grand Canyon II
Grand Canyon III
SoCJe2sn
NKT Victoria
NORTH SEA ATLANTIC
NORTH SEA GIANT
Seven Mar
|  | Array cable lay | Export cable lay | Cable burial | Rock installation/dumping | Trenching | Pull-in | ROV
Vessels with track record | With track record # | 28 | 3 | 5 | 6 |  | 0
Capable vessels | Capable vessels # | 45 | 7 | 146 | 110 | 69
Vessel type value potential per GW | Operation value opportunity right hand scale MNOK | 421.155 | 541.485 | 86.2365 | 17.4478 | 155.2257 | 38.1045 | 12.0731
|  |  |  | k£ |  |  | LCC MNOK
|  |  |  | low | high | Days | Catalyst | Day rate based
I.5 | Sum Offshore cable installation |  | 105.6867 |  |  |  | 0 | 1271.7277
5.1 | Export cable laying vessel | CLV | 45 | 175 | 300 | 150 |  | 541.485 | 200 | km cable | 0 | km interconnection | 2 | km day | 30 | WoW | 20 | mob
5.1 | Array cable laying vessel, OCV | CLV | 35 | 175 | 300 | 116.6667 |  | 421.155 | 1 | arrays/day |  |  |  |  | 30 | WoW | 20 | mob
5.2 | Trenching | Trench vsl | 12.9 | 40 | 90 | 143.3333 |  | 155.2257 | 50% | of lay time |  |  |  |  | 0 | WoW | 10 | mob
5.2 | SOV for pull-in, clamping, termination works | SOV | 3.1667 | 15 | 25 | 126.6667 |  | 38.1045
5.2 | Cable burial | OCV | 7.1667 | 38 | 50 | 143.3333 |  | 86.2365 | same As Trenching
5.2 | Cable protection/Rock dumping | Rock dumper | 1.45 | 15 | 30 | 48.3333 |  | 17.4478 | 2 | arrays/day rock dumping | 10 | loading | 5 | days mob/transit
5.3 | Carousel | Carousel |  | 4 | 5 | 116.6667 |  | 0 | Same as Array cable layer
5.3 | Cable plough | [6 empty] | 0
5.3 | trenching ROV | ROV | 1.0033 | 5 | 7 | 143.3333 |  | 12.0731 | same As Trenching
5.2 | Vertical injector | [6 empty] | 0
5.3 | Jetting sled | [6 empty] | 0
| Export cable laying vessel | CLV | 45 | 175 | 300 | 150 |  | 541.485 | 200 | km cable | 0 | km interconnection | 2 | km day | 30 | WoW | 20 | mob
| Array cable laying vessel, OCV | OCV | 5.3333 | 38 | 50 | 106.6667 |  | 64.176 | 1 | arrays/day |  |  |  |  | 20 | WoW | 20 | mob
| Trenching | Trench vsl | 13.35 | 40 | 90 | 148.3333 |  | 160.6405 | 0.5 | of lay time |  |  |  |  | 10 | WoW | 10 | mob
| SOV for pull-in, clamping, termination works | SOV | 1.5 | 15 | 25 | 60 |  | 18.0495
| Cable burial | OCV | 7.4167 | 38 | 50 | 148.3333 |  | 89.2447 | same As Trenching
| Cable protection/Rock dumping | Rock dumper | 2.45 | 15 | 30 | 81.6667 |  | 29.4809 | 1 | arrays/day rock dumping | 10 | loading | 5 | days mob/transit
| Post lay survey | Larger survey vsl | 0.33333 | 5 | 10 | 33.3333 |  | 4.011 | 2 | FWT /day
| Carousel | Carousel | 0.53333 | 4 | 5 | 106.6667 |  | 6.4176 | Same as Array cable layer
| Cable plough | [6 empty] | 0
| trenching ROV | ROV | 1.0383 | 5 | 7 | 148.3333 |  | 12.4943 | same As Trenching
| Vertical injector | [6 empty] | 0
| Jetting sled | [6 empty] | 0

## 4.OSS, Found, WTG installation
[5 empty] | NOK/£ | 12.033
67
Main task |  | Substation installation AHTS / Tug) | FWT towing to site (AHTS/Tug) | Anchor and mooring lines installation (pre-lay | FWT hook-up | Accommodation service | Guard vessel | Rock dumping
Activity description |  | Transfer (towing) of the (semi-sub) substation from its quayside fabrication site. | Transfer (towing) of the FTW from its quayside fabrication site. |  |  | Hotell and catering for service personnel. | Securing the site and vehicels within during the construction. Monitor marine traffic near the construction site visually, with radar and AIS. Secure the site for external vessel approaches and guide them to safely get past the site.
Estimated dayrate |  | Tug: 5000-7000 £ AHTS: 8000-30.000 £ | Tug: 5000-7000 £ AHTS: 8000-30.000 £ | AHTS: 8000-30.000 £ | AHTS: 8000-30.000 £ | 15.000-25.000 £ | 3000-15.000£
Vessel |  | AHTS/Tug boat | AHTS/Tug boat + hold back tug boat | AHTS | AHTS | SOV /CSOV | Small PSV, "fishing vessel"
Vessel main characteristics |  | Bollard pull, Tug winches, towing pins, shark-jaw | Bollard pull, Tug winches, towing pins, shark-jaw | Large deck for the handling of boyancy/coupling elements. Bollard pull, Tug winches, towing pins, shark-jaw | Large deck for the handling of boyancy/coupling elements. Bollard pull, Tug winches, towing pins, shark-jaw | Vessel with POB 40+ . Good seakeeping for comfort and safety during all operations and in particular transfer of personell. Technicians' wellfare and effective rest is paramount . | Endurance seaworthiness combined with high service speeds.
Critical vessel equipment/technology |  | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt | Tug winches 450t og 500t DP-2, Bollard pull 300 mt | Tug winches 450t og 500t DP-2, Bollard pull 300 mt | W2W capability (3-3.5 m Hs) | Endurance > 30 days
Intl suppliers | [5 empty] | Esvagt
Norwegian suppliers | [5 empty] | Edda/Østensjø, Eidesvik, Subsea 7 (Moxie)
Market share
Trend/Opportunities
Nor Market potential
Sub-task/Equipment |  | Barge |  |  |  | W2W, Daughter craft in davit
filters in the vessel list activated |  | track record | track record | track record: | track record: | same track record as for fixed; | No confirmed, although this is not typically added in the traco record
Vessels - having been involved in wind project |  | MV Island Victory | MV Island Victory | MV Island Victory | MV Island Victory | AKOFS Seafarer
AKOFS Wayfarer
Deep Cygnus
Edda Flora
Far Sapphire
Far Scotia
Geo Barents
Larissa
MV Island Clipper
MV Island Condor
MV Island Crown
MV Island Diligence
Nor Valiant
Normand Carrier
Normand Jarl
Normand Jarstein
Normand Mermaid
Normand Prosper
Normand Sira
Olympic Ares
Olympic Artemis
Olympic Challenger
Olympic Commander
Olympic Delta
Olympic Intervention IV
Olympic Orion
Olympic Taurus
Olympic Triton
Polar King
Polar Prince
Polar Queen
Rem Inspector
Rem Saltire
Seaway Moxie
Siddis Mariner
Skandi Constructor
Stril Explorer
Stril Server
Vestland Cygnus
filters in the vessel list activated |  | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt. AHTS and Tug with bp >150mt | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt. AHTS and Tug with bp >150mt | Tug winches 450t og 500t DP-2, Bollard pull 300 mt | Tug winches 450t og 500t DP-2, Bollard pull 300 mt | W2W capability (3.5 m Hs) DP2, POB 40 | small PSV, tug, Not: AHTS, subsea, other expensive vessels
Vessels - capable of doing jobs |  | Bourbon Orca | Bourbon Orca | Skandi Hercules | Skandi Hercules | Volantis | Fosnakongen | Volantis
|  | Bourboun Arctic | Bourboun Arctic | Skandi Skansen | Skandi Skansen | Geograph | Fosna Neptun | Skandi Acergy
|  | BB Octopus | BB Octopus | Skandi Amazonas | Skandi Amazonas | Geoholm | Fosna Viking | Skandi Africa
|  | Skandi Admiral (ex. Northern Admiral) | Skandi Admiral (ex. Northern Admiral) | Skandi Iceman | Skandi Iceman | Skandi Acergy | Fosna Amon | Skandi Hawk
|  | Skandi Hercules | Skandi Hercules | Skandi Iguacu | Skandi Iguacu | Skandi Achiever | Fosna Aqua | Skandi Neptune
|  | Skandi Skansen | Skandi Skansen | Skandi Vega | Skandi Vega | Skandi Acu | Fjordbris | Skandi Niteroi
|  | Skandi Amazonas | Skandi Amazonas | MV Island Victory | MV Island Victory | Skandi Africa | Fosnakallen | Skandi Olinda
|  | Skandi Angra | Skandi Angra | KL Sandefjord | KL Sandefjord | Skandi Hawk | Fosna | Skandi Patagonia
|  | Skandi Atlantic | Skandi Atlantic | KL Saltfjord | KL Saltfjord | Skandi Niteroi | Fosna Atlas | Skandi Recife
|  | Skandi Bergen | Skandi Bergen | Normand Installer | Normand Installer | Skandi Olinda | Fosna Ares | Skandi Salvador
|  | Skandi Botafogo | Skandi Botafogo | Siem Topaz | Siem Topaz | Skandi Recife | Fosna Orion | Skandi Seven
|  | Skandi Emerald | Skandi Emerald | Siem Ruby | Siem Ruby | Skandi Salvador | Fosna Fighter | Skandi Singapore
|  | Skandi Fluminense | Skandi Fluminense | Siem Sapphire | Siem Sapphire | Skandi Seven | Fosna Triton | Skandi Skansen
|  | Skandi Hera | Skandi Hera | Normand Drott | Normand Drott | Skandi Singapore | Fosna Poseidon | Skandi Vinland
|  | Skandi Iceman | Skandi Iceman | Normand Prosper | Normand Prosper | Skandi Skansen | Fosna Flyer | Skandi Vitoria
|  | Skandi Iguacu | Skandi Iguacu |  |  | Skandi Vinland | Ocean Art | Skandi Hera
|  | Skandi Ipanema | Skandi Ipanema |  |  | Viking Neptun | Ocean Response | Viking Neptun
|  | Skandi Pacific | Skandi Pacific |  |  | Acergy Viking | Ocean Alden | Acergy Viking
|  | Skandi Paraty | Skandi Paraty |  |  | Seven Viking | Ocean Star | Seven Viking
|  | Skandi Peregrino | Skandi Peregrino |  |  | Polar Queen | Ocean Ness | Subsea Viking
|  | Skandi Rio | Skandi Rio |  |  |  | Ocean Don | Polar Queen
|  | Skandi Saigon | Skandi Saigon |  |  | Despina | Ocean Tay | Larissa
|  | Skandi Urca | Skandi Urca |  |  | Havila Phoenix | Ocean Marlin | Despina
|  | Skandi Vega | Skandi Vega |  |  | Havila Subsea | Ocean Osprey | Havila Phoenix
|  | Havila Mercury | Havila Mercury |  |  |  | Bourbon Calm | Havila Harmony
|  | Havila Mars | Havila Mars |  |  |  | Bourbon Clear | Havila Subsea
|  | Havila Venus | Havila Venus |  |  | MOU Island Constructor | Bourbon Front | MV Island Victory
|  | Havila Jupiter | Havila Jupiter |  |  | MOU Island Wellserver | Bourbon Hidra | MV Island Valiant
|  | Havila Neptune | Havila Neptune |  |  | MV Island Pride | Bourbon Mistral | MOU Island Frontier
|  | MV Island Victory | MV Island Victory |  |  | Siddis Sailor | Bourbon Monsoon | MOU Island Constructor
|  | MV Island Vanguard | MV Island Vanguard |  |  | Normand Installer | Bourbon Rainbow | MOU Island Wellserver
|  | MV Island Valiant | MV Island Valiant |  |  | BOA Sub C | Bourbon Sapphire | MV Ocean Intervention
|  | KL Sandefjord | KL Sandefjord |  |  |  | Bourbon Tampen | MV Island Pride
|  | KL Saltfjord | KL Saltfjord |  |  |  | Bourbon Topaz | Normand Clipper
|  | Normand Pioneer | Normand Pioneer |  |  | Grand Canyon | Bourbon Emerald | Normand Installer
|  | Normand Installer | Normand Installer |  |  | Connector | Bourbon Jade | Normand Flower
|  | BOA Sub C | BOA Sub C |  |  |  | Bourbon Oceanteam 101 | BOA Sub C
|  | Polar Prince | Polar Prince |  |  |  | Bourbon Opale | Polar King
|  | Olympic Zeus | Olympic Zeus |  |  | Olympic Commander | Southern Ocean (ex BO104) | Polar Prince
|  | Olympic Hercules | Olympic Hercules |  |  |  | Boris | Deep Cygnus
|  | Olympic Pegasus | Olympic Pegasus |  |  |  | Baut | Grand Canyon
|  | Siem Amethyst | Siem Amethyst |  |  |  | BB Worker | Connector
|  | Siem Opal | Siem Opal |  |  | Olympic Challenger | BB Supporter | Olympic Orion
|  | Siem Garnet | Siem Garnet |  |  |  | Banak | Olympic Zeus
|  | Siem Diamond | Siem Diamond |  |  |  | Barents | Olympic Taurus
|  | Siem Topaz | Siem Topaz |  |  | Edda Fauna | BB Server | Olympic Commander
|  | Siem Ruby | Siem Ruby |  |  |  | Borgoy | Olympic Triton
|  | Siem Aquamarine | Siem Aquamarine |  |  | Edda Freya | Boxer | Olympic Intervention IV
|  | Siem Sapphire | Siem Sapphire |  |  | Edda Sun | Bulldog | Olympic Ares
|  | Siem Emerald | Siem Emerald |  |  | Edda Fides | Bokn | Olympic Challenger
|  | Siem Pearl | Siem Pearl |  |  | Edda Mistral | BB Connector | Olympic Artemis
|  | Normand Drott | Normand Drott |  |  | Edda Passat | BB Coaster | Olympic Delta
|  | Normand Ferking | Normand Ferking |  |  |  | John | Edda Fauna
|  | Normand Prosper | Normand Prosper |  |  | Siem N-Sea | Bess | Edda Flora
|  | Normand Ranger | Normand Ranger |  |  | Siem Day | Baus | Edda Fjord
|  | Normand Scorpion | Normand Scorpion |  |  | Siem Barracuda | Belos | Edda Freya
|  | Normand Sirius | Normand Sirius |  |  | Siem Spearfish | Rombak | Edda Sun
|  | BOS Turquesa | BOS Turquesa |  |  | Siem Stingray | Balder | Rem Saltire
|  | BOS Turmalina | BOS Turmalina |  |  |  | Bukken | Siem N-Sea
|  | Far Sapphire | Far Sapphire |  |  |  | Bruse | Siem Marlin
|  | Normand Saracen | Normand Saracen |  |  |  | Max Mammut | Siem Day
|  | Far Sagaris | Far Sagaris |  |  | Normand Pacific | Bjønn | Siem Barracuda
|  | Far Scout | Far Scout |  |  | Far Superior | Bebe | Siem Spearfish
|  | Far Statesman | Far Statesman |  |  | Normand Fortress | Buddy | Siem Stingray
|  | Far Stream | Far Stream |  |  |  | Thor III | Siem Helix 1
|  | Far Sigma | Far Sigma |  |  | Normand Maximus | Brage | Siem Helix 2
|  | Far Senator | Far Senator |  |  | Normand Vision | Beagle | Normand Jarstein
|  | Far Sword | Far Sword |  |  | Normand Navigator | Bison | Normand Pacific
|  | Far Santana | Far Santana |  |  | Normand Sentinel | Bryteren | Far Superior
|  | Normand Atlantic | Normand Atlantic |  |  | Normand Frontier | Skandi Aukra | Normand Maximus
|  | Normand Borg | Normand Borg |  |  | Norman Energy | Skandi Barra | Normand Vision
|  | Normand Ivan | Normand Ivan |  |  | Far Samson | Skandi Buchan | Normand Navigator
|  | Normand Mariner | Normand Mariner |  |  | Normand Subsea | Skandi Caledonia | Normand Sentinel
|  | Normand Master | Normand Master |  |  | Normand Baltic | Skandi Captain | Normand Cutter
|  | Normand Neptun | Normand Neptun |  |  | Normand Commander | Skandi Feistein | Normand Frontier
|  | Normand Titan | Normand Titan |  |  | Normand Poseidon | Skandi Flora | Normand Subsea
|  | Far Sabre | Far Sabre |  |  | Normand Australis | Skandi Foula | Normand Baltic
|  | Far Scimitar | Far Scimitar |  |  |  | Skandi Gamma | Normand Mermaid
|  | Far Sound | Far Sound |  |  | Elektron | Skandi Kvitsøy | Normand Australis
|  | Far Sovereign | Far Sovereign |  |  | Seaway Aimery | Skandi Marøy | Far Saga
|  | Far Strait | Far Strait |  |  |  | Skandi Mongstad | Seven Arctic
|  | Lady Astrid | Lady Astrid |  |  | Seven Arctic | Skandi Nova | Seven Atlantic
|  | Lady Caroline | Lady Caroline |  |  | Seven Falcon | Skandi Rona | Seven Borealis
|  | Sea Panther | Sea Panther |  |  | Seven Pegasus | Skandi Sotra | Seven Cruzeiro
|  | Sea Tiger | Sea Tiger |  |  | Seven Viking | Skandi Texel | Seven Eagle
|  | Elang Laut 1 | Elang Laut 1 |  |  | Grant Candies | NS Orla | Seven Falcon
|  | Magne Viking | Magne Viking |  |  | Harvey Intervention | FS Frayja | Seven Inagha
|  | Njord Viking | Njord Viking |  |  | Normand Oceanic | Viking Queen | Seven Kestrel
|  | Loke Viking | Loke Viking |  |  | Normand Subsea | Viking Athene | Seven Oceans
|  | Brage Viking | Brage Viking |  |  | Simar Esperanca | Viking Avant | Seven Pacific
|  | Grand Canyon II | Grand Canyon II |  |  |  | Viking Energy | Seven Pegasus
|  | Grand Canyon III | Grand Canyon III |  |  | Grand Canyon II | Viking Lady | Seven Rio
[6 empty] | Grand Canyon III | Viking Prince | Seven Seas
[6 empty] | Rever Topaz | Viking Princess | Seven Sun
[6 empty] | Deep Arctic | Christina E | Seven Viking
[6 empty] | NORTH SEA ATLANTIC | Energy Duchess | Seven Waves
[6 empty] | NORTH SEA GIANT | Energy Empress | Grant Candies
[6 empty] | Skandi SANTOS | Energy Swan | Harvey Intervention
[7 empty] | Energy Scout | MMA Pinnacle
[7 empty] | Havila Charisma | Seven Vega
[7 empty] | Havila Borg | Normand Oceanic
[7 empty] | Havila Foresight | Normand Subsea
[7 empty] | Havila Fortune | Simar Esperanca
[7 empty] | Havila Crusader | Grand Canyon II
[7 empty] | Havila Commander | Grand Canyon III
Havila Aurora
Havila Fanø
Havila Herøy
Havila Clipper
Havila Troll
MV Island Defender
MV Island Endeavour
MV Island Empress
MV Island Duchess
MV Island Dragon
MV Island Crusader
MV Island Contender
MV Island Condor
MV Island Commander
MV Island Clipper
MV Island Champion
MV Island Chieftain
MV Island Challenger
MV Island Diligence
MV Island Crown
KL Brevikfjord
KL Barentsfjord
KL Brisfjord
KL Brofjord
Siddis Sailor
Siddis Mariner
Normand Pioneer
Deep Cygnus
Fob Swath 1
Fob Swath 2
Fob Swath 3
Fob Swath 4
Fob Swath 5
Fob Swath 6
Fob Swath 7
Fob Swath 8
Fob Swath 9
Fob Swath 10
Olympic Electra
Olympic Energy
Olympic Promoter
Olympic Elena
Edda Ferd
Edda Fram
Edda Frende
Edda Fjord
Edda Fides
Edda Mistral
Edda Passat
Ajax
Apex
Phenix
Tenax
Velox
Vortex
Audax
Dux
Lomax
Pax
Silex
Vivax
Topaz Tiamat
Rem Arctic
Rem Cetus
Rem Insula
Rem Mira
Rem Mistral
Rem Supplier
Rem Trader
Hemir Horizon
Hermi Fighter
Hermit Storm
Hermit Galaxy
Hermit Thunder
Hermit Power
Hermit Guardian
Hermit Prosper
Rem Eir
Rem Mist
Rem Hrist
Neptun Naiad
H U Sverdrup II
M/S Nautilus
M/S Nautilus Survey
M/S Nautilus Ocean
T/B Nautilus Balder
Siem Pilot
Siem Hanne
Siem Symphony
Siem Pride
Siem Thiima
Stril Mar
Stril Barents
Stril Luna
Stril Polar
Stril Orion
Stril Mermaid
Stril Odin
Strilmøy
Stril Pioner
Stril Merkur
Stril Herkules
Stril Poseidon
Stril Mariner
Strilborg
Far Scotia
Normand Arctic
Normand Aurora
Normand Carrier
Normand Falnes
Normand Flipper
Normand Fortune
Normand Leader
Norman Serenade
Norman Server
Normand Service
Normand Sitella
Normand Skimmer
Normand Skipper
Normand Springer
Normand Starling
Normand Sun
Normand Supporter
Normand Supra
Normand Surfer
Normand Swan
Normand Swift
Norman Sygna
Normand Titus
Norman Tortuga
Normand Naley
Far Scotsman
Far Searcher
Far Solitaire
Far Seeker
Far Spica
Far Swan
Far Symphony
Sea Falcon
Sea Flyer
Sea Forth
Sea Frost
Sea Spark
Sea Spear
Sea Tantalus
Sea Brasil
Normand Corona
Normand Provider
Normand Sira
Normand Supplier
Normand Trym
Norman Vibran
Far Spirit
Far Splendour
Far Strider
Sea Angler
Sea Bass
Sea Pollock
Sea Triumph
Sea Turbot
Sea Trout
Sea Witch
Seaway Moxie
Tronds Lax
Tronds Max
Juanita
Evita II
Tanux I
Tanux II
Tanux III
Evita II
Ocean Europe
Vestland Cygnus
Norside Supporter
Norsea Fighter
Ocean Duke
Coey Viking
Cooper Viking
Dina Merkur
Dina Scout
Farland
GUARD CELENA
Guard Supplier
Hermit PROTECTOR
Hermit Viking
ISLAND DUKE
ISLAND PATRIOT
Ocean Dee
Ocean Falcon
SANCO SCORPIO
SARTOR
Sea Goldcrest
SEA GULL
Siem Atlas
Siem Caetes (Built 2011)
Siem Giant
Siem Maragogi (Built 2014)
Siem Pendotiba (Built 2012)
Siem Piatã (Built 2011)
Troms Arcturus
TROMS CAPELLA
Troms Castor
Troms Fjord
Troms Lyra
Troms Mira
Troms Pollux
Troms Sirius
World Diamond
World Pearl
|  | Substation mooring installation | Substation and FWT towing to site | Anchor and mooring lines installation | Substation and FWT hook-up | Accommodation service (SOV) | Guard vessel | Rock dumping
Vessels with track record | # | 1 | 1 | 1 | 1 | 39 | 0 | 0
Capable vessels | # | [5 empty] | 314
Capable vessels AHTS | # | 89 | 89 | 16 | 16 | 116 |  | 105
Capable vessels Tug | # | 3 | 13
Capable PSV for support |  |  |  | 199
Vessel type value potential per GW right hand scale | MNOK | 17.3275 | 115.3965 | 77.0112 | 239.6974 | 40.3105 | 36.2795 | 23.4643
|  | ok | ok |  | OK
Mooring installation |  | day rate k£ | [5 empty] | LCC day rate based
|  | low | high | FTW units | anchor /unit | days/anchor | Mob days incl transit | k£ | MNOK(£)
Anchor installation (crane) | OCV | 38 | 50 | 67 | 4 | 0.3 | 5 | 3250 | 39.1073
Mooring line installation (AHTS) | AHTS | 8 | 30 | 67 | 4 | 0.5 | 5 | 3150 | 37.9039
Substation anchor installation | OCV | 38 | 50 | 1 | 8 | 1 | 10 | 900 | 10.8297
Substation mooring line inst | AHTS | 8 | 30 | 1 | 8 | 1 | 10 | 540 | 6.4978
ROV | ROV | 5 | 7 | 67 | 4 | 0.5 | 5 | 735 | 8.8443
Rock dumping | Rock dumper | 15 | 30 | 67 | 4 | 0.3 | 5 | 1950 | 23.4643
Securing site | Guard vsl | 5 | 15 | 67 | 4 | 0.5 | 5 | 1575 | 18.952
[8 empty] | 12100 | 145.5993
Towing and installation |  | day rate £ |  | FTW/SS/anchors |  |  |  | LCC day rate based
| Vessel type | low | high | units | days /voyage or operation |  |  | k£ | MNOK(£)
Subtation towing, 3 off tugs | Tug | 5 | 7 | 3 | 10 |  |  | 210 | 2.5269
Substation hook-up | AHTS | 8 | 30 | 8 | 16 |  |  | 3840 | 46.2067 | 2 | days per anchor incl. WoW (1.5 m/s Hs). 8 anchors | 4 | mob+transit
FWT Towing pull | Tug | 5 | 7 | 67 | 10 |  |  | 4690 | 56.4348
FWT Towing hold-back | Tug | 5 | 7 | 67 | 10 |  |  | 4690 | 56.4348
FWT Hook-up | AHTS | 8 | 30 | 268 | 2 |  |  | 16080 | 193.4906 | 2 | days per anchor incl. WoW (1.5 m/s Hs). 3 anchors | 4 | mob+transit | 4 | ANCHORS
Watch/ Securing site | Guard vsl | 5 | 15 | 67 | 3 |  |  | 3015 | 36.2795
Accommodation service (SOV) | SOV | 15 | 25 | 67 | 2 |  |  | 3350 | 40.3105 | to reach any FTW within 1 hr
[8 empty] | #VALUE! | 384.5346

## 5.O&M
Main task |  | WTG main component O&M | WTG general O&M / Access | Foundation and mooring I&R | Scour/hydrographic monitoring and management | Cable I&R | Substation maintenance and service | Accommodation/Access service
Activity description |  | Main component refurbishment, replacement and repair consists of the replacement of large components such as gearboxes, blades, transformers and generators. Replacement is carried out in harbour | Rapid transport of offshore personnel and smaller spare parts or tools. | Maintenance consists of visual inspections, non-destructive testing (NDT) and sea bed survey work with remedial service work completed when required. Internal and external Inspections with focus on structural integrity, lifting, safety equipment, corrosion protection and scour protection. External (secondary) structures may require cleaning from bird guano for health and safety reasons. | Seabed inspection and hydrographi survey by ROV, Autonomous Underwater Vehicle (AUV) or vessel. | Maintenance, repair and service record management. Cable repair will normally require a full cable laying spread. Inspection and repair/adjustment of boyancy modules involves the use of ROV. For array cables, shorter cable lengths and challenges in joining shorter cables mean that replacement of the cable may be more cost effective than repair. If so, the cable will be cut at the bases of the foundations, the internal section of cable removed, and a new cable laid using the same process as installation. | Primarily non-intrusive inspections of topside switchgear and transformers, sampling of transformer oil, semi-sub foundation and topside structural inspection and resulting infrequent service interventions. Cleaning, paint repairs and secondary steelwork repairs (for example to railings, gratings, gates, stairs and ladders). Large repair operations, such as replacing transformers, require heavy lift vessels. Access to the substation may be by vessel or helicopter but since few failures require urgent attention, the weather downtime of vessels may not be an important consideration, as it is for turbines. | Hotell and catering for service personnel.
Typical vessel |  | AHTS (current solution)/ Other (future) |  | SOV for launching CTV/daughter craft. | SOV for launching ROV /AUV. (AUV may be launched from smaller craft/CTV) | Cable layer for replacement. Otherwise general Offshore construction vessel. | Crane vessel for replacement/repair of heavy components. CSOV | SOV /CSOV
Vessel main characteristics |  | Bollard pull, Tug winches, towing pins, shark-jaw | Fender system at the bow helps the vessel to approach the access ladder of a wind turbine or an accommodation vessel and enables the personnel transported to embark safely. Speed |  |  |  |  | Vessel with POB 40+ . Good seakeeping for comfort and safety during all operations and in particular transfer of personell. Technicians' wellfare and effective rest is paramount. A dedicated , permanent gnagway for personnel and tools transfer (W2W) with operability in 3.5+ m Hs and allowing transfer between two floating/moving objects.
Critical vessel equipment/technology |  | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt | Speed > 30 kts Fenders >12 PAX | W2W capability (3.5 m Hs) |  | DP-2, (break-back) tensioners , ROV hangar. A-frame /Deck crane for postioning of ploughs/trench cutting machines and work-class ROV and quadrant deployment frame. Operability in 3m Hs | DP2 W2W. Crane>25 mt; no age limit | W2W capability (3.5 m Hs) DP2 POB 40 "Zero-emission" (features reducing ALARP emission, documented)
Intl suppliers | [7 empty] | Esvagt
Norwegian suppliers | [7 empty] | Edda/Østensjø, Eidesvik
Market share
Trend/Opportunities |  | It is assumed that future parks will be based on performing the replacement at site. Towing to port will be to expensive. | [5 empty] | Increased requirements for optimization in fuel economy for OW operations. Increased requirements for optimized deck layout, storage areas and equipment to fit technicians operational workflow.
Nor Market potential
Sub-task |  | Personnel transport/access |  |  |  |  | Personnel transport/access | W2W, Daughter craft in davit
filters in the vessel list activated |  | No track record | No track record | No track record | No track record | No track record | No track record | Same track reocrd as for fixed
Fob Swath 1
Fob Swath 2
Fob Swath 3
Fob Swath 4
Fob Swath 5
Fob Swath 6
Fob Swath 7
Fob Swath 8
|  |  | Fob Swath 9 |  |  |  |  | AKOFS Seafarer
AKOFS Wayfarer
|  |  | AKOFS Seafarer |  |  |  |  | Deep Cygnus
|  |  | AKOFS Wayfarer |  |  |  |  | Edda Flora
|  |  | Deep Cygnus |  |  |  |  | Far Sapphire
|  |  | Edda Flora |  |  |  |  | Far Scotia
|  |  | Far Sapphire |  |  |  |  | Geo Barents
|  |  | Far Scotia |  |  |  |  | Larissa
Vessels - having been involved in wind project |  |  | Geo Barents |  |  |  |  | MV Island Clipper
|  |  | Larissa |  |  |  |  | MV Island Condor
|  |  | MV Island Clipper |  |  |  |  | MV Island Crown
|  |  | MV Island Condor |  |  |  |  | MV Island Diligence
|  |  | MV Island Crown |  |  |  |  | Nor Valiant
|  |  | MV Island Diligence |  |  |  |  | Normand Carrier
|  |  | Nor Valiant |  |  |  |  | Normand Jarl
|  |  | Normand Carrier |  |  |  |  | Normand Jarstein
|  |  | Normand Jarl |  |  |  |  | Normand Mermaid
|  |  | Normand Jarstein |  |  |  |  | Normand Prosper
|  |  | Normand Mermaid |  |  |  |  | Normand Sira
|  |  | Normand Prosper |  |  |  |  | Olympic Ares
|  |  | Normand Sira |  |  |  |  | Olympic Artemis
|  |  | Olympic Ares |  |  |  |  | Olympic Challenger
|  |  | Olympic Artemis |  |  |  |  | Olympic Commander
|  |  | Olympic Challenger |  |  |  |  | Olympic Delta
|  |  | Olympic Commander |  |  |  |  | Olympic Intervention IV
|  |  | Olympic Delta |  |  |  |  | Olympic Orion
|  |  | Olympic Intervention IV |  |  |  |  | Olympic Taurus
|  |  | Olympic Orion |  |  |  |  | Olympic Triton
|  |  | Olympic Taurus |  |  |  |  | Polar King
|  |  | Olympic Triton |  |  |  |  | Polar Prince
|  |  | Polar King |  |  |  |  | Polar Queen
|  |  | Polar Prince |  |  |  |  | Rem Inspector
|  |  | Polar Queen |  |  |  |  | Rem Saltire
|  |  | Rem Inspector |  |  |  |  | Seaway Moxie
|  |  | Rem Saltire |  |  |  |  | Siddis Mariner
|  |  | Seaway Moxie |  |  |  |  | Skandi Constructor
|  |  | Siddis Mariner |  |  |  |  | Stril Explorer
|  |  | Skandi Constructor |  |  |  |  | Stril Server
|  |  | Stril Explorer |  |  |  |  | Vestland Cygnus
Stril Server
Vestland Cygnus
filters in the vessel list activated |  | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt. AHTS with bp >150mt | Using same requirements as for fixed: W2W capability (3.m Hs) DP2 POB 40 "Zero-emission" (features reducing ALARP emission, documented) -> only vessels built after 2005 Including the vessels which have track record for fixed as well. | DP2 ROV hangar , W2W AHTS: Bollard pull>300 mt | DP2 ROV hangar , crane>25 mt , deck >500 m2 | Using same requirements as for fixed: DP-2, ROV hangar. A-frame /Deck crane for postioning of ploughs/trench cutting machines and work-class ROV and quadrant deployment frame. (Deck>500m2), Crane > 25 ton) Operability in 3m Hs. Including the vessels which have track record for fixed as well. | This differs wrt fixed, i.e. if larger parts needs replacement, it could be cheaper to un-hook det unit and tow it to shore. However, on site work is assumed to be done by the same type of vessels as for fixed. For the towing part, the same vessels as for FWT (complete WTG with foundation) towing to site are assumed to do the work: | Same vessels as for fixed:(this theory has only been used for W2W, not other work scope, can be discussed)
Vessels - capable of doing jobs | AHTS 300mt | Skandi Hercules | Fob Swath 10 (newbuild) | Ocean Alden | Bourbon Emerald |  | Bourbon Calm
|  | Skandi Skansen |  | Bourbon Emerald | Bourbon Oceanteam 101 |  | Bourbon Clear
|  | Skandi Amazonas | Volantis | Bourbon Oceanteam 101 | Deep Vision |  | Bourbon Front | Volantis
|  | Skandi Iceman | Geograph | Volantis | Dina Star |  | Bourbon Rainbow | Geograph
|  | Skandi Iguacu | Geoholm | Deep Vision | Skandi Neptune | Skandi Niteroi | Bourbon Emerald | Geoholm
|  | Skandi Vega | Skandi Acergy | Dina Star | Geoholm | Skandi Patagonia | Bourbon Jade | Skandi Acergy
|  | KL Sandefjord | Skandi Achiever | Skandi Neptune | Geosea | Skandi Salvador | Bourbon Oceanteam 101 | Skandi Achiever
|  | KL Saltfjord | Skandi Acu | Geoholm | Geosund | Skandi Seven | Southern Ocean (ex BO104) | Skandi Acu
|  | Siem Amethyst | Skandi Africa | Geosea | Skandi Acergy | Skandi Singapore | Volantis | Skandi Africa
|  | Siem Opal | Skandi Hawk | Geosund | Skandi Achiever | Skandi Skansen | Deep Vision | Skandi Hawk
|  | Siem Topaz | Skandi Niteroi | Skandi Acergy | Skandi Acu | Viking Neptun | Dina Star | Skandi Niteroi
|  | Siem Ruby | Skandi Olinda | Skandi Achiever | Skandi Africa | Acergy Viking | Skandi Neptune | Skandi Olinda
|  | Siem Sapphire | Skandi Recife | Skandi Africa | Skandi Buzios | Seven Viking | Geoholm | Skandi Recife
|  | Normand Drott | Skandi Salvador | Skandi Carla | Skandi Carla | Subsea Viking | Geosea | Skandi Salvador
|  | Normand Prosper | Skandi Seven | Skandi Chieftain | Skandi Chieftain | Polar Queen | Geosund | Skandi Seven
|  |  | Skandi Singapore | Skandi Constructor | Skandi Darwin | Larissa | Skandi Acergy | Skandi Singapore
| AHTS 150 to 300 | Skandi Angra | Skandi Skansen | Skandi Darwin | Skandi Hawk | Despina | Skandi Achiever | Skandi Skansen
|  | Skandi Atlantic | Skandi Vinland | Skandi Hawk | Skandi Neptune | Havila Phoenix | Skandi Acu | Skandi Vinland
|  | Skandi Bergen | Viking Neptun | Skandi Hugen | Skandi Niteroi | Havila Harmony | Skandi Africa | Viking Neptun
|  | Skandi Botafogo | Acergy Viking | Skandi Neptune | Skandi Patagonia | Havila Subsea | Skandi Buzios | Acergy Viking
|  | Skandi Emerald | Seven Viking | Skandi Niteroi | Skandi Salvador | MOU Island Frontier | Skandi Carla | Seven Viking
|  | Skandi Fluminense | Polar Queen | Skandi Patagonia | Skandi Seven | MOU Island Constructor | Skandi Chieftain | Polar Queen
|  | Skandi Hera |  | Skandi Salvador | Skandi Singapore | MOU Island Wellserver | Skandi Darwin
|  | Skandi Pacific | Despina | Skandi Seven | Skandi Skansen | MV Ocean Intervention | Skandi Hawk | Despina
|  | Skandi Paraty | Havila Phoenix | Skandi Singapore | Skandi Vinland | MV Island Pride | Skandi Neptune | Havila Phoenix
|  | Skandi Peregrino | Havila Subsea | Skandi Skansen | Viking Neptun | Normand Clipper | Skandi Niteroi | Havila Subsea
|  | Skandi Rio |  | Skandi Vinland | Acergy Viking | Normand Installer | Skandi Olinda
|  | Skandi Saigon |  | Viking Neptun | Seven Viking | Normand Flower | Skandi Patagonia
|  | Skandi Urca | MOU Island Constructor | Acergy Viking | Subsea Viking | BOA Sub C | Skandi Recife | MOU Island Constructor
|  | Havila Mercury | MOU Island Wellserver | Seven Viking | Polar Onyx | Polar King | Skandi Salvador | MOU Island Wellserver
|  | Havila Mars | MV Island Pride | Subsea Viking | Polar Queen | Polar Prince | Skandi Seven | MV Island Pride
|  | Havila Venus | Siddis Sailor | Polar Onyx | Larissa | Deep Cygnus | Skandi Singapore | Siddis Sailor
|  | Havila Jupiter | Normand Installer | Polar Queen | Despina | Grand Canyon | Skandi Skansen | Normand Installer
|  | Havila Neptune | BOA Sub C | Larissa | Havila Phoenix | Connector | Skandi Vinland | BOA Sub C
|  | MV Island Vanguard |  | Despina | Havila Harmony | Olympic Orion | Skandi Vitoria
|  | MV Island Valiant |  | Havila Phoenix | Havila Subsea | Olympic Taurus | Skandi Hera
|  | Olympic Zeus | Grand Canyon | Havila Harmony | MV Island Victory | Olympic Commander | Viking Neptun | Grand Canyon
|  | Siem Garnet | Connector | Havila Subsea | MV Island Valiant | Olympic Triton | Acergy Viking | Connector
|  | Siem Diamond |  | MV Island Victory | MOU Island Frontier | Olympic Intervention IV | Seven Viking
|  | Siem Aquamarine |  | MV Island Valiant | MOU Island Constructor | Olympic Ares | Subsea Viking
|  | Siem Emerald | Olympic Commander | MOU Island Frontier | MOU Island Wellserver | Olympic Challenger | Polar Onyx | Olympic Commander
|  | Siem Pearl |  | MOU Island Constructor | MV Ocean Intervention | Olympic Artemis | Polar Queen
|  | Normand Ferking |  | MOU Island Wellserver | MV Island Pride | Olympic Delta | Larissa
|  | Normand Ranger |  | MV Ocean Intervention | Normand Clipper | Edda Fjord | Despina
|  | Normand Scorpion | Olympic Challenger | MV Island Pride | Normand Pioneer | Edda Freya | Havila Phoenix | Olympic Challenger
|  | Normand Sirius |  | Skagerak | Normand Installer | Rem Saltire | Havila Harmony
|  | Far Sapphire |  | Normand Clipper | Normand Flower | Siem N-Sea | Havila Subsea
|  | Normand Saracen | Edda Fauna | Normand Pioneer | BOA Sub C | Siem Day | MV Island Victory | Edda Fauna
|  | Far Sagaris |  | Normand Installer | Polar King | Siem Barracuda | MV Island Valiant
|  | Far Statesman | Edda Freya | Normand Flower | Polar Prince | Siem Spearfish | MV Island Diligence | Edda Freya
|  | Far Stream | Edda Sun | BOA Sub C | Deep Cygnus | Siem Stingray | MV Island Crown | Edda Sun
|  | Far Sigma | Edda Fides | Polar King | Grand Canyon | Normand Jarstein | MOU Island Frontier | Edda Fides
|  | Far Senator | Edda Mistral | Polar Prince | Connector | Normand Maximus | MOU Island Constructor | Edda Mistral
|  | Far Sword | Edda Passat | Deep Cygnus | Olympic Orion | Normand Vision | MOU Island Wellserver | Edda Passat
|  | Far Sabre |  | Grand Canyon | Olympic Zeus | Normand Navigator | MV Ocean Intervention
|  | Far Scimitar | Siem N-Sea | Connector | Olympic Taurus | Normand Sentinel | MV Island Pride | Siem N-Sea
|  | Far Sound | Siem Day | Olympic Orion | Olympic Commander | Normand Cutter | Normand Clipper | Siem Day
|  | Far Strait | Siem Barracuda | Olympic Zeus | Olympic Triton | Normand Frontier | Normand Pioneer | Siem Barracuda
|  | Elang Laut 1 | Siem Spearfish | Olympic Taurus | Olympic Intervention IV | Normand Subsea | Normand Installer | Siem Spearfish
|  | Magne Viking | Siem Stingray | Olympic Commander | Olympic Ares | Normand Baltic | Normand Flower | Siem Stingray
|  | Njord Viking |  | Olympic Triton | Olympic Challenger | Normand Mermaid | BOA Sub C
|  | Loke Viking |  | Olympic Intervention IV | Olympic Artemis | Normand Australis | Polar King
|  | Brage Viking |  | Olympic Ares | Olympic Delta | Far Saga | Polar Prince
|  |  | Normand Pacific | Olympic Challenger | Edda Fauna | Elektron | Deep Cygnus | Normand Pacific
|  |  | Far Superior | Olympic Artemis | Edda Flora | Seven Atlantic | Grand Canyon | Far Superior
|  | Audax | Normand Fortress | Olympic Delta | Edda Fjord | Seven Falcon | Connector | Normand Fortress
|  | Dux |  | Edda Fauna | Edda Freya | Seven Inagha | Olympic Orion
|  | Pax | Normand Maximus | Edda Flora | Edda Sun | Seven Kestrel | Olympic Zeus | Normand Maximus
|  |  | Normand Vision | Edda Fjord | Rem Saltire | Seven Pegasus | Olympic Taurus | Normand Vision
|  |  | Normand Navigator | Edda Freya | Siem N-Sea | Seven Viking | Olympic Commander | Normand Navigator
|  |  | Normand Sentinel | Edda Sun | Siem Day | Grant Candies | Olympic Triton | Normand Sentinel
|  |  | Normand Frontier | Edda Fides | Siem Barracuda | Harvey Intervention | Olympic Intervention IV | Normand Frontier
|  |  | Norman Energy | Rem Saltire | Siem Spearfish | Normand Oceanic | Olympic Ares | Norman Energy
|  |  | Far Samson | Siem N-Sea | Siem Stingray | Normand Subsea | Olympic Challenger | Far Samson
|  |  | Normand Subsea | Siem Day | Normand Jarstein | Simar Esperanca | Olympic Artemis | Normand Subsea
|  |  | Normand Baltic | Siem Barracuda | Normand Ocean | Grand Canyon II | Olympic Delta | Normand Baltic
|  |  | Normand Commander | Siem Spearfish | Normand Pacific | Grand Canyon III | Edda Fauna | Normand Commander
|  |  | Normand Poseidon | Siem Stingray | Far Superior | Deep Arctic | Edda Flora | Normand Poseidon
|  |  | Normand Australis | Stril Merkur | Normand Maximus | NORTH SEA GIANT | Edda Fjord | Normand Australis
|  |  |  | Stril Herkules | Normand Vision | Seven Mar | Edda Freya
|  |  | Elektron | Stril Server | Normand Navigator | Skandi SANTOS | Edda Sun | Elektron
|  |  | Seaway Aimery | Stril Explorer | Normand Sentinel |  | Edda Fides | Seaway Aimery
|  |  |  | Normand Jarstein | Normand Cutter |  | Topaz Tiamat
|  |  | Seven Arctic | Normand Ocean | Normand Frontier |  | Rem Saltire | Seven Arctic
|  |  | Seven Falcon | Far Scotia | Normand Subsea |  | Siem Pilot | Seven Falcon
| TUG |  | Seven Pegasus | Normand Pacific | Normand Baltic |  | Siem N-Sea | Seven Pegasus
|  |  | Seven Viking | Far Superior | Normand Mermaid |  | Siem Day | Seven Viking
|  |  | Grant Candies | Normand Maximus | Normand Australis |  | Siem Barracuda | Grant Candies
|  |  | Harvey Intervention | Normand Vision | Far Saga |  | Siem Spearfish | Harvey Intervention
|  |  | Normand Oceanic | Normand Navigator | Elektron |  | Siem Stingray | Normand Oceanic
|  |  | Normand Subsea | Normand Sentinel | Seven Arctic |  | Siem Amethyst | Normand Subsea
|  |  | Simar Esperanca | Normand Cutter | Seven Atlantic |  | Siem Opal | Simar Esperanca
|  |  |  | Normand Frontier | Seven Eagle |  | Siem Garnet
|  |  | Grand Canyon II | Normand Subsea | Seven Falcon |  | Siem Diamond | Grand Canyon II
|  |  | Grand Canyon III | Normand Baltic | Seven Inagha |  | Siem Topaz | Grand Canyon III
|  |  | Rever Topaz | Normand Mermaid | Seven Kestrel |  | Siem Ruby | Rever Topaz
|  |  | Deep Arctic | Normand Australis | Seven Pegasus |  | Siem Aquamarine | Deep Arctic
|  |  | NORTH SEA ATLANTIC | Far Saga | Seven Viking |  | Siem Sapphire | NORTH SEA ATLANTIC
|  |  | NORTH SEA GIANT | Elektron | Grant Candies |  | Siem Emerald | NORTH SEA GIANT
|  |  | Skandi SANTOS | Seven Arctic | Harvey Intervention |  | Siem Pearl | Skandi SANTOS
|  |  |  | Seven Atlantic | Normand Oceanic |  | Normand Jarstein
|  |  |  | Seven Falcon | Normand Subsea |  | Normand Ocean
|  |  |  | Seven Inagha | Simar Esperanca |  | Normand Jarl
|  |  |  | Seven Kestrel | Grand Canyon II |  | Normand Pacific
|  |  |  | Seven Pegasus | Grand Canyon III |  | Far Superior
|  |  |  | Seven Viking | Deep Arctic |  | Normand Fortress
|  |  |  | Grant Candies | NORTH SEA ATLANTIC |  | Nor Valiant
|  |  |  | Harvey Intervention | NORTH SEA GIANT |  | Normand Maximus
|  |  |  | Normand Oceanic | Skandi SANTOS |  | Normand Vision
|  |  |  | Normand Subsea |  |  | Normand Navigator
|  |  |  | Simar Esperanca |  |  | Normand Sentinel
| 150 to 300 |  |  | Grand Canyon II |  |  | Normand Cutter
|  |  |  | Grand Canyon III |  |  | Normand Frontier
|  |  |  | Deep Arctic |  |  | Norman Energy
|  |  |  | NORTH SEA ATLANTIC |  |  | Normand Jarl
|  |  |  | NORTH SEA GIANT |  |  | Far Samson
|  |  |  | Skandi SANTOS |  |  | Normand Subsea
Normand Flower
Normand Progress
Normand Baltic
Normand Commander
Normand Mermaid
Normand Poseidon
Normand Australis
Far Saga
Elektron
Seaway Aimery
Seven Arctic
Seven Atlantic
Seven Cruzeiro
Seven Falcon
Seven Inagha
Seven Kestrel
Seven Navica
Seven Oceans
Seven Pacific
Seven Pegasus
Seven Rio
Seven Seas
Seven Sun
Seven Viking
Seven Waves
Grant Candies
Harvey Intervention
Seven Vega
Normand Oceanic
Normand Subsea
Simar Esperanca
Vestland Cygnus
Ocean Fortune
Ocean Duke
Grand Canyon II
Grand Canyon III
Rever Topaz
Deep Arctic
NKT Victoria
NORTH SEA ATLANTIC
NORTH SEA GIANT
Skandi SANTOS
|  | WTG main component O&M AHTS+OCV+Tug+ PSV) | WTG general O&M (SOV) | Foundation and mooring I&R (OCV+PSV) | Scour/hydrographic monitoring and management | Cable I&R (OCV+PSV) | Substation maintenance and service (OCV+ PSV) | Accommodation/Access service
Vessels with track record | # | 0 | 39 | 0 | 0 | 0 | 0 | 37
Capable vessels AHTS | # | 16 |  | 15
Capable vessels OCV |  |  |  | 117 | 109 | 77 | 159
Capable vessels Tug (incl. AHTS) |  | 92
Capable vessels PSV |  | 199
Capable vessels CTV |  |  | 9
Capable vessels SOV |  |  | 117 |  |  |  |  | 114
Vessel type value potential per GW | MNOK | 452.4408 | 210.5775 | 597.4792 | 286.1875 | 632.625 | 239.9 | 2260
|  | ok | ok | ok |  | ok
12.05
25
|  |  |  | dayrate k£ |  | units | days | MNOK/yr | Catalyst M£/GW/yr | LCC day rate based MNOK/GW
O |  |  |  | low | high |  |  |  | 75
O.1 | Operations (25M£/yr) |  | 8.2125 |  |  |  |  | 98.821 | 0 | 2260
1.3 | Offshore logistics (Hotel and access) | [7 empty] | 0
| SOV | SOV | 8.2125 | 15 | 25 | 1 | 300.5 | 98.821 |  | 2260 | 0.9 | presence, reduced for planned maintenance days
| CTV | CTV | 0 | 2.5 | 3 | 2 | 0 | 0 |  | 0
0
O.2 | Maintenance (50 M£/yr)
2.1 | Turbine maintance and service | [6 empty] | 18.0976 |  | 452.4408
Main
| Main component repair (with climbing crane on found) | PSV | 0.2144 | 10 | 20 | 1.7867 | 6 | 2.5799 |  | 64.4969
| Blade replacement ("not possible at site") | Tug | 0.0616 | 5 | 7 | 0.88 | 10 | 0.74123 |  | 18.5308 | every 3 Main comp repair | 24 hrs operation + mob/demob
| Unhook, hook-up, lay-down | AHTS | 0.264 | 8 | 30 | 0.88 | 10 | 3.1767 |  | 79.4178 | every 3 Main comp repair, 3 anchors, 2 days each incl. WoW (1.5 m/s Hs), 4 days mob + transit
| Cable handling | OCV | 0.264 | 38 | 50 | 0.88 | 6 | 3.1767 |  | 79.4178 | every 3 Main comp repair, 4 days mob + transit
General WTG maintenance and repair
| General WTG maintenance and repair | General maintainance byWTG technicians teams, acces through SOV | [5 empty] | 0 |  | 0
| Additional SOV for planned maintenance | SOV | 0.7 | 15 | 25 | 1 | 28 | 8.4231 |  | 210.5775
Alternative: tug to harbour for major repair/replacement
| Main component replacement (in harbour) | Tug | 0 | 5 | 7 | 2.6667 | 0 | 0 |  | 0 | 10 days
| Replacement operation (in harbour) | WiV | 0 | 90 | 130 | 2.6667 | 0 | 0 |  | 0 | 1 day
| AHTS (unhook, hook-up, lay-down) | AHTS | 0 | 8 | 30 | 2.6667 | 0 | 0 |  | 0 | 1 day + tug service (10 days) =11
| Cable handling | OCV | 0 | 38 | 50 | 2.6667 | 0 | 0 |  | 0 | 1 day + mob+ transit=2
2.2 | BoP maintenance and service (18M£/yr) | [6 empty] | 74.7502 | 5 | 1868.7542
597.4792 | Found I&R | OCV | 0.66667 | 38 | 50 | 66.6667 | 0.5 | 20.0833 |  | 502.0833 | Double scope BFOW, 50% subsea
|  | ROV | 0.11667 | 5 | 7 | 66.6667 | 0.25 | 1.4058 |  | 35.1458
| Occasional foundation repair | OCV | 0.2 | 38 | 50 | 2 | 2 | 2.41 |  | 60.25 | "Event" basis
135.5625 | Mooring monitoring | PSV | 0.33333 | 10 | 20 | 66.6667 | 0.25 | 4.0167 |  | 100.4167 | Primarily subsea
|  | ROV | 0.11667 | 5 | 7 | 66.6667 | 0.25 | 1.4058 |  | 35.1458
286.1875 | Anchor scour and hydrographic monitoring | PSV | 0.33333 | 38 | 50 | 66.6667 | 0.25 | 10.0417 |  | 251.0417 | Primarily subsea
|  | ROV | 0.11667 | 5 | 7 | 66.6667 | 0.25 | 1.4058 |  | 35.1458
632.625 | Cable I&R | OCV | 0.66667 | 38 | 50 | 66.6667 | 0.5 | 20.0833 |  | 502.0833 | Primarily subsea
|  | ROV | 0.23333 | 5 | 7 | 66.6667 | 0.5 | 2.8117 |  | 70.2917
| Occasional cable repair | OCV | 0.2 | 38 | 50 | 2 | 2 | 2.41 |  | 60.25 | "Event" basis
239.9 | Subst I&R | PSV | 0.4 | 10 | 20 | 1 | 20 | 4.82 |  | 120.5 | 50% subsea
|  | ROV | 0.07 | 5 | 7 | 1 | 10 | 0.8435 |  | 21.0875
| Ocassional Substation repair | OCV | 0.25 | 38 | 50 | 1 | 5 | 3.0125 |  | 75.3125 | "Event" basis
23 | Substation hevy repair | Towing spread | [7 empty] | 23 | incl in Subst maintenance
13.4198

## 6.Decom
Decom
Decommissioning includes towing of WTG and/or substation into harbour for complete dismantling. It also includes the recovery of anchors, mooring lines and cables. For nacelle, tower components, steel structures and electrical components (in WTG/Substation), the potential for recycling is considerable. There is no current process for recycling composite materials such as those used in the blades and nacelle cover, but is likely that methods will emerge by the time a large volume of offshore wind turbine commissioning is required.
Main task |  | WTG (incl. Foundation) decom | Mooring /Anchor recovery | Cable removal/recovery | Substation decom | Pre/Post decom Environmental survey | Re-powering | Life extension
Activity description |  | Reverse of installation process: transfer to shore for decom |  | Cables are disconnected at each end then pulled from the sea bed and wound on to drums or chopped into short sections for storage on the decommissioning vessel | Reverse of installation process: transfer to shore for decom | Hydographic survey to | Re-power the site with new (larger) turbines, likely meaning decommissioning of existing turbines, foundations and array cables, with the possibility to extend the life of electrical transmission assets. The MW rating of the wind farm and transmission system may be unchanged as the area of the wind farm and density of turbines (MW installed per square km) are likely to be unchanged. Substation may in case be re-used. | Extend the operational life of existing assets through a programme of risk assessments, inspections, addressing regulatory aspects, and some component replacement.
Vessel |  | AHTS | AHTS | Cable installation vessel | AHTS
Vessel main characteristics |  | Bollard pull: ? MN | Bollard pull: ? MN |  | Bollard pull: ? MN
Critical vessel equipment/technology |  | Tug winches, DP-2 | Tug winches, DP-2 |  | Tug winches, DP-2
Intl suppliers |  |  | Mærsk, Swire, Tidewater, Bourbon | Boskalis, Global Marine and Subsea 7, VanOrd(Nexus), JdN, Nexans (Aurora), CRS Holland, Pharos Offshore and Subsea Environmental Services | Boskalis, Saipem and Seaway Heavy Lifting (Subsea 7)
Norwegian suppliers
Market share
Trend/Opportunities |  | O&G decom methods/tonnage may apply | O&G decom methods/tonnage may apply
Nor Market potential
Sub-task/Equipment |  | Personell access (W2W), DP
filters in the vessel list activated |  | no track record | no track record | no track record | no track record | no track record | no track record | no track record
Vessels - having been involved in wind project
filters in the vessel list activated |  | Same vessels as for installation: Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt. AHTS and Tug with bp >150mt | Same vessels as for installation: Tug winches 450t og 500t DP-2, Bollard pull 300 mt | Same as for fixed: Assuming this can be done by vessels which can handle array cable installation or export cable installation: | Tug winches 450t og 500t.DP-2, Bollard Pull 150mt Hold-back tugboat bollard pull 100 mt. AHTS and Tug with bp >150mt | Assumed same vessels as for geotechnical and geophysical: Included: AHTS with ROV, construction with ROV, PSV with potential A-frame (ROV in container), subsea with ROV Not included: smaller vessels, vessel with no crane nor potential a-frame
Vessels - capable of doing jobs |  | Bourbon Orca | MV Island Victory | BOA Sub C | Bourbon Orca
|  | MV Island Victory | Skandi Hercules | C/V Fjordkabel | Bourboun Arctic | Larissa
|  | Bourboun Arctic | Skandi Skansen | Connector | BB Octopus | Despina
|  | BB Octopus | Skandi Amazonas | Deep Cygnus | Skandi Admiral (ex. Northern Admiral) | Havila Subsea
|  | Skandi Admiral (ex. Northern Admiral) | Skandi Iceman | Edda Flora | Skandi Hercules | MV Island Pride
|  | Skandi Hercules | Skandi Iguacu | Edda Freya | Skandi Skansen | Polar King
|  | Skandi Skansen | Skandi Vega | Elektron | Skandi Amazonas | Olympic Zeus
|  | Skandi Amazonas | KL Sandefjord | Grand Canyon | Skandi Angra | Olympic Taurus
|  | Skandi Angra | KL Saltfjord | Grand Canyon II | Skandi Atlantic | Olympic Commander
|  | Skandi Atlantic | Normand Installer | Grand Canyon III | Skandi Bergen | Olympic Intervention IV
|  | Skandi Bergen | Siem Topaz | Havila Jupiter | Skandi Botafogo | Olympic Ares
|  | Skandi Botafogo | Siem Ruby | Havila Phoenix | Skandi Emerald | Olympic Challenger
|  | Skandi Emerald | Siem Sapphire | Larissa | Skandi Fluminense | Olympic Artemis
|  | Skandi Fluminense | Normand Drott | Nexans Aurora | Skandi Hera | Olympic Delta
|  | Skandi Hera | Normand Prosper | Normand Clipper | Skandi Iceman | Edda Flora
|  | Skandi Iceman |  | Normand Cutter | Skandi Iguacu | Stril Server
|  | Skandi Iguacu |  | Normand Frontier | Skandi Ipanema | Ocean Art
|  | Skandi Ipanema |  | Normand Jarstein | Skandi Pacific | Ocean Alden
|  | Skandi Pacific |  | Normand Maximus | Skandi Paraty | Ocean Star
|  | Skandi Paraty |  | Normand Navigator | Skandi Peregrino | Ocean Ness
|  | Skandi Peregrino |  | Normand Oceanic | Skandi Rio | Ocean Don
|  | Skandi Rio |  | Normand Pioneer | Skandi Saigon | Ocean Tay
|  | Skandi Saigon |  | Normand Sentinel | Skandi Urca | Ocean Marlin
|  | Skandi Urca |  | Normand Vision | Skandi Vega | Ocean Osprey
|  | Skandi Vega |  | Normand Vision | Havila Mercury | Bourboun Arctic
|  | Havila Mercury |  | Olympic Ares | Havila Mars | Skandi Carla
|  | Havila Mars |  | Olympic Artemis | Havila Venus | Skandi Vinland
|  | Havila Venus |  | Olympic Challenger | Havila Jupiter | Skandi Amazonas
|  | Havila Jupiter |  | Olympic Commander | Havila Neptune | Skandi Angra
|  | Havila Neptune |  | Olympic Delta | MV Island Victory | Skandi Atlantic
|  | MV Island Victory |  | Olympic Intervention IV | MV Island Vanguard | Skandi Bergen
|  | MV Island Vanguard |  | Olympic Taurus | MV Island Valiant | Skandi Botafogo
|  | MV Island Valiant |  | Olympic Triton | KL Sandefjord | Skandi Emerald
|  | KL Sandefjord |  | Olympic Zeus | KL Saltfjord | Skandi Fluminense
|  | KL Saltfjord |  | Polar King | Normand Pioneer | Skandi Hera
|  | Normand Pioneer |  | Polar Onyx | Normand Installer | Skandi Iceman
|  | Normand Installer |  | Polar Prince | BOA Sub C | Skandi Iguacu
|  | BOA Sub C |  | Polar Prince | Polar Prince | Skandi Ipanema
|  | Polar Prince |  | Rem Inspector | Olympic Zeus | Skandi Pacific
|  | Olympic Zeus |  | Rem Saltire | Olympic Hercules | Skandi Paraty
|  | Olympic Hercules |  | Seaway Aimery | Olympic Pegasus | Skandi Peregrino
|  | Olympic Pegasus |  | Seven Arctic | Siem Amethyst | Skandi Rio
|  | Siem Amethyst |  | Seven Borealis | Siem Opal | Skandi Saigon
|  | Siem Opal |  | Seven Cruzeiro | Siem Garnet | Skandi Urca
|  | Siem Garnet |  | Seven Eagle | Siem Diamond | Skandi Vega
|  | Siem Diamond |  | Seven Pacific | Siem Topaz | Skandi Aukra
|  | Siem Topaz |  | Seven Rio | Siem Ruby | Skandi Barra
|  | Siem Ruby |  | Seven Seas | Siem Aquamarine | Skandi Buchan
|  | Siem Aquamarine |  | Seven Sun | Siem Sapphire | Skandi Caledonia
|  | Siem Sapphire |  | Seven Waves | Siem Emerald | Skandi Captain
|  | Siem Emerald |  | Siem Barracuda | Siem Pearl | Skandi Feistein
|  | Siem Pearl |  | Siem Day | Normand Drott | Skandi Flora
|  | Normand Drott |  | Siem Spearfish | Normand Ferking | Skandi Foula
|  | Normand Ferking |  | Siem Stingray | Normand Prosper | Skandi Gamma
|  | Normand Prosper |  | Skagerak | Normand Ranger | Skandi Kvitsøy
|  | Normand Ranger |  | Skandi Acergy | Normand Scorpion | Skandi Marøy
|  | Normand Scorpion |  | Skandi Acu | Normand Sirius | Skandi Mongstad
|  | Normand Sirius |  | Skandi Africa | BOS Turquesa | Skandi Nova
|  | BOS Turquesa |  | Skandi Buzios | BOS Turmalina | Skandi Rona
|  | BOS Turmalina |  | Skandi Constructor | Far Sapphire | Skandi Sotra
|  | Far Sapphire |  | Skandi Neptune | Normand Saracen | Skandi Texel
|  | Normand Saracen |  | Skandi Niteroi | Far Sagaris | NS Orla
|  | Far Sagaris |  | Skandi Olinda | Far Scout | FS Frayja
|  | Far Scout |  | Skandi Recife | Far Statesman | Seven Viking
|  | Far Statesman |  | Skandi Vitoria | Far Stream | Viking Queen
|  | Far Stream |  | Subsea Viking | Far Sigma | Viking Athene
|  | Far Sigma |  | Viking Neptun | Far Senator | Viking Avant
|  | Far Senator |  | Volantis | Far Sword | Viking Energy
|  | Far Sword |  | Deep Arctic | Far Santana | Viking Lady
|  | Far Santana |  | NKT Victoria | Normand Atlantic | Viking Prince
|  | Normand Atlantic |  | NORTH SEA ATLANTIC | Normand Borg | Viking Princess
|  | Normand Borg |  | NORTH SEA GIANT | Normand Ivan | Christina E
|  | Normand Ivan |  | Seven Mar | Normand Mariner | Polar Queen
|  | Normand Mariner |  |  | Normand Master | Energy Duchess
|  | Normand Master |  |  | Normand Neptun | Energy Empress
|  | Normand Neptun |  |  | Normand Titan | Larissa
|  | Normand Titan |  |  | Far Sabre | Despina
|  | Far Sabre |  |  | Far Scimitar | Energy Swan
|  | Far Scimitar |  |  | Far Sound | Energy Scout
|  | Far Sound |  |  | Far Sovereign | Havila Mercury
|  | Far Sovereign |  |  | Far Strait | Havila Mars
|  | Far Strait |  |  | Lady Astrid | Havila Venus
|  | Lady Astrid |  |  | Lady Caroline | Havila Jupiter
|  | Lady Caroline |  |  | Sea Panther | Havila Neptune
|  | Sea Panther |  |  | Sea Tiger | Havila Charisma
|  | Sea Tiger |  |  | Elang Laut 1 | Havila Borg
|  | Elang Laut 1 |  |  | Magne Viking | Havila Foresight
|  | Magne Viking |  |  | Njord Viking | Havila Fortune
|  | Njord Viking |  |  | Loke Viking | Havila Crusader
|  | Loke Viking |  |  | Brage Viking | Havila Commander
|  | Brage Viking |  |  | Grand Canyon II | Havila Aurora
|  | Grand Canyon II |  |  | Grand Canyon III | Havila Fanø
|  | Grand Canyon III |  |  |  | Havila Herøy
Havila Clipper
Havila Troll
MV Island Defender
MV Island Endeavour
MV Island Empress
MV Island Duchess
MV Island Dragon
MV Island Crusader
MV Island Contender
MV Island Condor
MV Island Commander
MV Island Clipper
MV Island Champion
MV Island Chieftain
MV Island Challenger
MV Island Victory
MV Island Vanguard
MV Island Diligence
MV Island Crown
KL Brevikfjord
KL Barentsfjord
KL Brisfjord
KL Brofjord
KL Sandefjord
KL Saltfjord
Siddis Sailor
Siddis Mariner
Normand Pioneer
Olympic Orion
Olympic Taurus
Olympic Commander
Olympic Electra
Olympic Artemis
Olympic Delta
Olympic Hercules
Olympic Pegasus
Olympic Energy
Olympic Promoter
Olympic Elena
Edda Ferd
Edda Fram
Edda Frende
Edda Fjord
Edda Fides
Edda Mistral
Edda Passat
Topaz Tiamat
Rem Arctic
Rem Cetus
Rem Insula
Rem Mira
Rem Mistral
Rem Supplier
Rem Trader
Hemir Horizon
Hermi Fighter
Hermit Storm
Hermit Galaxy
Hermit Thunder
Hermit Power
Hermit Guardian
Hermit Prosper
Rem Eir
Rem Mist
Rem Hrist
Neptun Naiad
H U Sverdrup II
M/S Nautilus Survey
Siem Pilot
Siem Hanne
Siem Symphony
Siem Pride
Siem Thiima
Siem N-Sea
Siem Marlin
Siem Amethyst
Siem Opal
Siem Garnet
Siem Diamond
Siem Topaz
Siem Ruby
Siem Aquamarine
Siem Sapphire
Siem Emerald
Siem Pearl
Stril Mar
Stril Barents
Stril Luna
Stril Polar
Stril Orion
Stril Mermaid
Stril Odin
Strilmøy
Stril Pioner
Stril Merkur
Stril Herkules
Stril Poseidon
Stril Mariner
Strilborg
Stril Server
Stril Explorer
Far Scotia
Normand Jarl
Normand Pacific
Far Superior
Normand Fortress
Nor Valiant
Normand Drott
Normand Ferking
Normand Prosper
Normand Ranger
Normand Scorpion
Normand Sirius
Normand Topazio
Nor Captain
Nor Spring
BOS Turquesa
BOS Turmalina
Far Sapphire
Normand Saracen
Far Sagaris
Far Scout
Far Statesman
Far Stream
Far Sigma
Far Senator
Far Sword
Far Santana
Normand Atlantic
Normand Borg
Normand Ivan
Normand Mariner
Normand Master
Normand Neptun
Normand Titan
Far Sabre
Far Scimitar
Far Sound
Far Sovereign
Far Strait
Lady Astrid
Nor Tigerfish
Lady Caroline
Sea Ocelot
Sea Panther
Sea Tiger
Elang Laut 1
Normand Arctic
Normand Aurora
Normand Carrier
Normand Falnes
Normand Flipper
Normand Fortune
Normand Leader
Norman Serenade
Norman Server
Normand Service
Normand Sitella
Normand Skimmer
Normand Skipper
Normand Springer
Normand Starling
Normand Sun
Normand Supporter
Normand Supra
Normand Surfer
Normand Swan
Normand Swift
Norman Sygna
Normand Titus
Norman Tortuga
Normand Naley
Far Scotsman
Far Searcher
Far Solitaire
Far Seeker
Far Spica
Far Swan
Far Symphony
Sea Falcon
Sea Flyer
Sea Forth
Sea Frost
Sea Spark
Sea Spear
Sea Tantalus
Sea Brasil
Normand Corona
Normand Provider
Normand Sira
Normand Supplier
Normand Trym
Norman Vibran
Far Spirit
Far Splendour
Far Strider
Sea Angler
Sea Bass
Sea Pollock
Sea Triumph
Sea Turbot
Sea Trout
Sea Witch
Elektron
Seaway Aimery
Seaway Moxie
Normand Oceanic
Juanita
Evita II
Tanux I
Tanux II
Tanux III
Evita II
[6 empty] | Ocean Europe | [7 empty] | a
Vestland Cygnus
Norside Supporter
Norsea Fighter
Ocean Duke
Magne Viking
Njord Viking
Loke Viking
Brage Viking
Coey Viking
Cooper Viking
ARTEMIS ANGLER
ARTEMIS ARCTIC
ARTEMIS ATHENE
ARTEMIS ATLANTIC
ARTEMIS ODYSSEY
ATLANTIC GUARDIAN
Deep Arctic
Dina Merkur
Dina Scout
Farland
GUARD CELENA
Guard Supplier
Hermit PROTECTOR
Hermit Viking
Hugin Explorer
ISLAND DUKE
ISLAND PATRIOT
NKT Victoria
NORTH SEA ATLANTIC
NORTH SEA GIANT
Ocean Dee
Ocean Falcon
OCEANIC SIRIUS
OCEANIC VEGA
PGS Apollo
Polar Duchess
Polar Duke
Polar Marquis
Polarcus Adira
Polarcus Alima
Polarcus Asima
Polarcus Nadia
Polarcus Naila
Ramform Atlas
Ramform Challenger
Ramform Explorer
Ramform Hyperion
Ramform Sovereign
Ramform Tethys
Ramform Titan
Ramform Valiant
Ramform Vanguard
Ramform Victory
Ramform Viking
Rig Andromeda
SANCO ATLANTIC
SANCO CHASER
SANCO SCORPIO
SANCO SEA
SANCO SKY
SANCO SPIRIT
SANCO STAR
SANCO SWIFT
SANCO SWORD
SARTOR
Sea Goldcrest
SEA GULL
Seven Mar
Siem Atlas
Siem Caetes (Built 2011)
Siem Giant
Siem Maragogi (Built 2014)
Siem Marataizes (Built 2016)
Skandi SANTOS
SW Amundsen
SW Cook
SW EMPRESS
Troms Arcturus
TROMS CAPELLA
Troms Castor
Troms Fjord
Troms Lyra
Troms Mira
Troms Pollux
Troms Sirius
World Diamond
World Pearl
|  | FTW/Substation removal (AHTS/Tug) | Mooring /Anchor recovery (AHTS/OCV) | Cable removal/recovery (OCV) | Substation removal (AHTS/OCV) | Pre/Post decom Environmental survey | Guard vessel
Vessels with track record | #
Capable vessels | # | 93 | 15 | 73 | 92 | 393 | 300
AHTS | # | 50 | 10
Tug | # | 10
OCV | # | 33 | 5 | 68
Vessel type value potential per GW right hand scale | MNOK | 195.3838 | 103.4838 | 87.1724 |  | 6.0165 | 15.6429
|  |  |  | 1£ | 12.033 | NOK
| Decom - Removal (Marine ops) |  |  |  | Dayrate k£ |  |  |  |  | 304.2156
[5 empty] | low | high | #Units | Anchors/unit | Days/anchor (line)
| Sum FWT removal |  | 15.1333 | [6 empty] | 182.0994
| Mooring un-hook |  | 1.8 | AHTS | 8 | 30 | 66.6667 | 3 | 0.3 | 21.6594
| Mooring removal |  | 1.8 | AHTS | 8 | 30 | 66.6667 | 3 | 0.3 | 21.6594
| Anchor removal (OCV) |  | 5 | OCV | 38 | 50 | 66.6667 | 3 | 0.5 | 60.165
| Towing , pull |  | 3.2667 | Tug | 5 | 7 | 66.6667 |  | 7 | 39.3078 | 1 | day per unit
| Towing, Hold-back |  | 3.2667 | Tug | 5 | 7 | 66.6667 |  | 7 | 39.3078 | 1 | per unit
| Sum Substation removal |  | 1.104 | [6 empty] | 13.2844
| Mooring un-hook |  | 0.222 | AHTS | 8 | 30 | 1 | 8 | 0.3 | 2.6713
| Mooring removal |  | 0.222 | AHTS | 8 | 30 | 1 | 8 | 0.3 | 2.6713
| Anchor removal, subsea removal |  | 0.45 | OCV | 38 | 50 | 1 | 8 | 0.5 | 5.4148
| Towing (3 off tugs) |  | 0.21 | Tug | 5 | 7 | 3 |  | 10 | 2.5269
| Cable removal |  | 7.2444 | [6 empty] | 87.1724
| Export cable: Cutting, lifting |  | 4.3333 | OCV | 38 | 50 | 86.6667 |  |  | 52.143 | 3 | km/day | 200 | km cable | 10 | WoW | 10 | Mob
| Array cable : cutting, lifting |  | 2.1111 | OCV | 38 | 50 | 42.2222 |  |  | 25.403 | 3 | array/day | 200 | km cable | 10 | WoW | 10 | Mob
| Carousel |  | 0.5 | Carousel | 4 | 5 | 100 |  |  | 6.0165
| Carousel |  | 0.3 | Carousel | 4 | 5 | 60 |  |  | 3.6099
| General : securing site |  | 1.3 |  |  |  | 50 |  |  | 15.6429
| Securing site |  | 1.3 | Guard vsl | 5 | 15 | 86.6667 |  |  | 15.6429 |  | 1 day per unit + prep 20 days
| Pre/Post removal survey |  | 0.5 |  |  |  | 50 |  |  | 6.0165
|  |  | 0.5 | Larger survey vsl | 5 | 10 | 50 |  |  | 6.0165

## Survey plot
|  | Environmental survey | Resource/metocean survey: buoy and sensor installation and operation | Geophysical/Geotechnical and hydrographical survey
Vessels with track record | # | 1 | 1 | 15
Capable vessels | # | 41 | 383 | 301
Vessel type value potential per GW | MNOK | 43.3188 | 19.2528 | 65.7002

## Project logistics plot
|  | Heavy transport - blades | Heavy transport - towers/foundations/TP | Heavy transport - nacelles
Vessels with track record | # | 12 | 6 | 9
Capable vessels | # | 35 | 29 | 32
Vessel type value potential per GW | MNOK | 23.0633 | 65.3459 | 6.0165

## FWT construction plot
|  | FWT positioning (Tug) | Mooring prelay/hook-up (AHTS) | FWT construction (Crane vessel) | Securing site (guard vsl) | Construction barge
Vessels with track record | # | 0 | 0 | 0 | 0 | 0
Capable vessels | # | 13 | 16 | 8 | 0 | 0
Vessel type value potential per GW right hand scale | MNOK | 22.4616 | 51.0199 | 320.88 | 65.8807 | 48.132

## Cable lay plot
| Array cable lay | Export cable lay | Cable burial | Rock installation/dumping | Trenching | Pull-in | ROV
With track record # | 28 | 3 | 5 | 6 | 0 | 0 | 0
Capable vessels # | 45 | 7 | 146 | 110 | 69 | 0 | 0
Operation value opportunity right hand scale MNOK | 421.155 | 541.485 | 86.2365 | 17.4478 | 155.2257 | 38.1045 | 12.0731

## 5.Installation plot
|  | Substation mooring installation (same as for FWT and common sum of value)? | Substation and FWT towing to site | Anchor and mooring lines installation | Substation and FWT hook-up | Accommodation service (SOV) | Guard vessel | Rock dumping
Vessels with track record | # | 1 | 1 | 1 | 1 | 39 | 0 | 0
Capable vessels | # | 0 | 0 | 0 | 0 | 0 | 314 | 0
Capable vessels AHTS | # | 89 | 89 | 16 | 16 | 116 | 0 | 105
Capable vessels Tug | # | 3 | 13 | 0 | 0 | 0 | 0 | 0
Capable PSV for support |  | 0 | 0 | 199 | 0 | 0 | 0 | 0
Vessel type value potential per GW right hand scale | MNOK | 17.3275 | 115.3965 | 77.0112 | 239.6974 | 40.3105 | 36.2795 | 23.4643

## 6. OMS plot
|  | WTG main component O&M AHTS+OCV+Tug+ PSV) | WTG general O&M (SOV) | Foundation and mooring I&R (OCV+PSV) | Scour/hydrographic monitoring and management | Cable I&R (OCV+PSV) | Substation maintenance and service (OCV+ PSV) | Accommodation/Access service
Vessels with track record | # | 0 | 39 | 0 | 0 | 0 | 0 | 37
Capable vessels AHTS | # | 16 | 0 | 15 | 0 | 0 | 0 | 0
Capable vessels OCV |  | 0 | 0 | 117 | 109 | 77 | 159 | 0
Capable vessels Tug (incl. AHTS) |  | 92 | 0 | 0 | 0 | 0 | 0 | 0
Capable vessels PSV |  | 199 | 0 | 0 | 0 | 0 | 0 | 0
Capable vessels CTV |  | 0 | 9 | 0 | 0 | 0 | 0 | 0
Capable vessels SOV |  | 0 | 117 | 0 | 0 | 0 | 0 | 114
Vessel type value potential per GW | MNOK | 452.4408 | 210.5775 | 597.4792 | 286.1875 | 632.625 | 239.9 | 2260

## 7. Decom plot
|  | FTW/Substation removal (AHTS/Tug) | Mooring /Anchor recovery (AHTS/OCV) | Cable removal/recovery (OCV) | Substation removal (AHTS/OCV) | Pre/Post decom Environmental survey | Guard vessel
Vessels with track record | # | 0 | 0 | 0 | 0 | 0 | 0
Capable vessels | # | 93 | 15 | 73 | 92 | 393 | 300
AHTS | # | 50 | 10 | 0 | 0 | 0 | 0
Tug | # | 10 | 0 | 0 | 0 | 0 | 0
OCV | # | 33 | 5 | 68 | 0 | 0 | 0
Vessel type value potential per GW right hand scale | MNOK | 195.3838 | 103.4838 | 87.1724 | 0 | 6.0165 | 15.6429

## Abbreviations
Vessel type |  | Main features | Operability/Limitations
SOV | Service and Operation Vessel | Hotel and maintenance equipment including deck crane and W2W arrangement. Equipped with a redundant DP system.
CSOV
WIV | WTG installation vessel | Jack-up with large deck space with deck loading capacity. Crane for heavy and high lifts (1000 mt +/100 m+ ab deck) with small minimum radius
FIV | Foundation Installation Vessel | Crane Auxiliary cranes Dynamic positioning system Propulsion systems Jack-up system Spud cans Helideck Gangway
CLV | Cable Laying Vessel | Dedicated cabel laying vessel with large deck space for heavy load, ROV spread, crane and/or quadrant handling tool
OCV | Offshore Contruction vessel
AHTS | Anchor Handling Tug Supply vessel
Equipment
ROV | Remotely Operated Vehicle
AUV | Autonomously Operated Vehicle
DP | Dynamic Positioning
W2W | Walk to Work | Personell transfer gangway with active compensation for vessel and/or floating structures movement.
LARS
Windfarm components
MP | Monopile
TP | Transition Piece
OSS | Offshore SubStation
FWT | Floating Wind Turbine
Other marine terms
POB | Persons on board
Other industry terms
CPT
UXO
CPS
Operators
OHT | Offshore Heavy Lift
JdN
SHL | Seaway Heavy Lift
OI | Ocean Installer
OIM | OIM Wind ltd (Oddgeir Indrestrand Marine)
Soruces | BVG associates, Renvewable UK, FOWIC

## CAPEX
[5 empty] | International |  |  |  |  | Norway
|  |  |  | min | max | bc | spread |  | min | max | mean
Substation installation | 5% | incl. Manufacturing | Surveys
Foundation and WTG installation | 5% |  | Project logistics |  |  |  | 0% |  |  |  |  | 0%
Anchor installation | 7% | incl manufacturing | Export cable installation | 25% | 35% | 30% | 10% |  | 32.5% | 67.5% |  | 35%
| 8% | incl manufacturing | Export cable supply | 5% | 15% | 10% | 10% |  | 32.5% | 67.5% |  | 35%
Export cable installation | 4% | incl manufacturing | Array cable installation
|  |  | Mooring (inst + supply) |  |  |  | 0% |  | 0% | 22.75% |  | 22.75%
Substation installation
OPEX | 25% |  | WTG/Found installation | 3.6% | 16.4% | 10% | 12.8% |  | 50% | 90% |  | 40%
|  |  | O&M (WTG, BoP) | 6.8% | 13.2% | 10% | 6.4% |  | 45% | 95% |  | 50%
|  |  | Decom |  |  |  | #REF! |  |  |  |  | 0%
[7 empty] | #REF! |  |  |  |  | 0%
[5 empty] | WTG /Found inst | Mooring | Array cable | OSS | Export cable supply | Expoer cable inst
|  |  | Material |  |  | 50 | 50 | 75 | 85
|  |  | Repair and installation service |  |  | 30 | 25 |  |  | 60
|  |  | Construction works |  |  |  |  | 10 |  | 15
|  |  | Water transport |  |  | 5 | 5 |  |  | 10
|  |  | Legal |  |  | 5 | 5 | 5 | 5 | 5
|  |  | Engineering |  |  | 10 | 15 | 10 | 10 | 10
[5 empty] | 100 | 100 | 100 | 100 | 100 | 100
Norwegian marketshare Bottom-fixed WF | 3-5% | Norsk industri, Norges Rederiforbund, NORWEA, 2017)
Future Norwegian marketshare FOWF | >20%
Norwegian marketshare Bottom fixed WF | same as Bottom-fixed as per today
6
30
85
121
6%
6
17%
6
basis10%